## Cover
Oracle Alumni Network Portal - Project Plan (CPMAI)
Cognitive Project Management for AI ¦ Business > Data > Modeling > Evaluation > Deployment > Monitoring
CPMAI Golden Rule: AI Success = Business + Data + Technology + Adoption ¦ Portal Adaptation: Business + Data + Design + Adoption
Document control
Project / Program Name | Oracle Alumni Network Portal - Creation
Client / Organization | Oracle
Executive Sponsor (CXO) | [Executive Sponsor - CXO]
Project Manager | [Project Manager]
Product Owner / Design Lead | [Product Owner / Design Lead]
Source Board | OAN Portal Delivery Board (Plan V3.2, iteration 9, 13 Oct 2026) + APEX Build Pack V1.1 (Q31) + Functional Specification v1.1
Application / Stack | Oracle APEX 26.1.5 on dev (Q32); ORDS; OAN_APP workspace
Plan Scope | 16 sprints S0-S15 - 11 gates - 154 tracked tasks - 319.75 pd (before 20% contingency)
Delivery Window | 19 Oct 2026 (S0) to 28 May 2027 (end S15)
Document Reference | OAN-PLAN-V3.2
Version | 3.2
Status | Baseline for CXO review
Last Updated | 2026-10-13
Classification | [Internal / Confidential]
Frameworks applied
CPMAI - Cognitive Project Management for AI (PMI): Business Understanding > Data Understanding > Modeling > Evaluation > Deployment > Monitoring
Spec-Driven Development (SDD): the Functional Specification v1.1 and APEX Build Pack V1.1 are the governing specs; the build follows Build Pack wave order (Q31) with Build Pack page numbers
Delivery board discipline: 16 sprints S0-S15, 11 gates incl. go-live 8.0, 154 tracked tasks, velocity-based capacity with a 20% contingency
Build options are gated: each option (AI assistant, channels, Careers feed) is built in DEV and switched on in PROD only after its DPIA annex and external agreement (G-AI, G-CH, G-CF)
Priority tiers P0-P4 from docs/05-flow-priority.md: P0 and P1 are never cut; the S11 descope lane cuts from P4 upward
Scope decisions applied: no Oracle HR brokering (Q29), no Oracle logos (Q30)
Responsible AI / privacy gate: Legal - Ethical - Secure - Explainable - Valuable (alumni PII, consent and a DPIA per option)
Oracle brand foundations: Oracle Red #C74634 - Ink #201E1C - Charcoal #312D2A - Canvas #FCFBFA
WCAG 2.2 AA accessibility target across all screens and 4 breakpoints
RACI / RASCI accountability, RAID log discipline and an explicit gate checklist
Baseline: OAN Portal Delivery Board, Plan V3.2 / iteration 9 (13 Oct 2026) - 16 sprints S0-S15, 11 gates, 154 tracked tasks, 319.75 pd. Governing specs: Functional Specification v1.1 and APEX Build Pack V1.1 (Q31). Stack: APEX 26.1.5 on dev (Q32), ORDS. Frameworks: CPMAI (PMI) and Spec-Driven Development.

## ReadMe
ReadMe - How to use this workbook
Purpose, tab guide, CPMAI reference, and the keys and definitions used throughout.
Purpose | This workbook is the single planning and governance control point for the Oracle Alumni Network Portal. It is aligned to the OAN Portal Delivery Board (Plan V3.2, iteration 9, 13 Oct 2026): 16 sprints S0-S15, 11 gates including go-live 8.0, 154 tracked tasks and 319.75 pd of development estimate before the 20% contingency.
How to use | 1) Confirm the Delivery Board and Gate Checklist. 2) Work the Kanban Board sprint by sprint. 3) Close each gate before the next stage. 4) Plan capacity on the Sprint Capacity Planner and log actuals weekly. 5) Review RAID weekly. 6) Report value at the Steering Committee using the KPI Dashboard.
Sprint cadence | Setup and design run in S0 (19-30 Oct 2026); build runs S1-S11 in Build Pack wave order (Q31); S12-S13 cover hardening, UAT, go-live; S14-S15 cover the pilot, hypercare and handover. Capacity per sprint is planned on the Sprint Capacity Planner and every closed sprint is logged on the Sprint Performance Tracker.
Update cadence | Plan and board: weekly and at every gate. Sprint Performance Tracker: at each sprint close. Gate Checklist: per gate. KPI Dashboard and Success Plan: monthly. RAID Log: weekly. Artefact Register: on every artefact version change.
Golden Rule | CPMAI Golden Rule: AI Success = Business + Data + Technology + Adoption ¦ Portal Adaptation: Business + Data + Design + Adoption
Source of truth | The attached OAN Portal Delivery Board defines the plan baseline: S0 19-30 Oct 2026 to S15 17-28 May 2027, 11 gates (G0, G1, G-RB, G-AI, G-CH, G-CF, G2, G3, G4, G5, 8.0), 154 tracked tasks and 319.75 pd. Card status comes from task_plan.md in the GitHub repository.
Tab guide
Tab | What it is for | Owner
Cover | Document control, the plan baseline and the frameworks applied. | PM
ReadMe | Purpose, tab guide, CPMAI reference, keys and definitions. | PM
Lifecycle Roadmap | The CPMAI phases mapped to the 16 sprints S0-S15 and the 11 board gates. | PM / Product Owner
Setup & Design Plan | Setup and design work inside the S0-S1 window (19 Oct - 13 Nov 2026), feeding gate G0. | PM
CXO Governance | Governance bodies, decision rights, cadence, escalation and the CXO decision log. | Executive Sponsor
Success Plan | Goals and measures of success, success criteria, adoption plan and benefits realisation. | Product Owner
Change & Adoption | Change strategy, stakeholder analysis, impact assessment, comms plan, training plan and ADKAR readiness tracker. | Change & Comms Lead
Value Stream Map | As-is alumni engagement value stream, flow efficiency, pain points and opportunities by stage. | UX Lead / Product Owner
KPI Dashboard | Reconnect, re-engage, re-hire, self-serve, quality, delivery and board-delivery KPIs with baselines and targets. | Product Owner
RACI Matrix | Accountability for every activity across all roles, including the sprint and gate activities. | PM
RAID Log | Risks, Assumptions, Issues and Dependencies aligned to the board - G0 blockers, gated options, descope lane. | PM / Risk Owner
Artefact Register | Every programme artefact including the delivery board and dashboards, with version, owner and status. | PM
Sprint Roadmap | The 16 sprints S0-S15 and the 11 gates - what each sprint delivers and its gate. | Scrum Master / Delivery Lead
Sprint Capacity Planner | Velocity-based capacity model for the current sprint with a planning-risk buffer. | Scrum Master / Delivery Lead
Sprint Performance Tracker | Closed-sprint log with completion, utilisation, 3-sprint trend and next-sprint forecast. | Scrum Master / Delivery Lead
Delivery Board | The 16 sprints and 11 gates from the attached board with dates, scope, task counts, dev pd and gate alignment. | PMO / Delivery Lead
Gate Checklist | Every gate, its due date, status and pass condition - G0 to G5 plus the gated build options and go-live 8.0. | PMO / Product Owner
Board Tasks | The tracked card list (id, task, category, dev pd, priority tier, status) that drives the Kanban Board and Dashboard. | Scrum Master / Delivery Lead
Kanban Board | One card per work item in the six board status columns, with card count and dev pd per column. | Scrum Master / Delivery Lead
Kanban Dashboard | Flow metrics: cards and dev effort by status, by category and by priority tier, with charts. | Scrum Master / Delivery Lead
Sprint Planner Dashboard | Capacity and performance charts ported from the attached Sprint Capacity Planner and linked to the sprint tabs. | PMO / Delivery Lead
Delivery Board | The 16 sprints S0-S15 and 11 gates from the attached delivery board, with dates, scope, task counts, dev effort and gate alignment. | PMO / Delivery Lead
Gate Checklist | Every gate, its due date, status and pass condition - G0 through G5 plus the gated build options (G-AI, G-CH, G-CF), re-baseline (G-RB) and go-live 8.0. | PMO / Product Owner
Kanban Board | Visual delivery board - one card per work item in the six status columns of the attached board, with card count and dev pd per column. | Scrum Master / Delivery Lead
Board Tasks | The tracked card list (id, task, category, dev pd, priority tier, status) that drives the Kanban Board and Kanban Dashboard. | Scrum Master / Delivery Lead
Kanban Dashboard | Live flow metrics: cards and dev effort by status, by category and by priority tier, with charts. | Scrum Master / Delivery Lead
Sprint Planner Dashboard | Capacity and performance charts ported from the attached Sprint Capacity Planner & Performance Tracker.xlsx, linked to the sprint tabs. | PMO / Delivery Lead
Status Report | Live project status as of 15 Oct 2026 (iteration 23): progress, board status distribution, workstream progress, decisions needed and next steps. | Product Owner / PMO
Delivered Pages | The 73 pages already live on dev, grouped by area. | Delivery Lead
CI-CD Pipeline | The four pipeline stages, the pipeline items and their state, and the manual dev deploy. | DevOps / Delivery Lead
CPMAI lifecycle - quick reference
# | CPMAI Phase | Core Question | What it means
1 | Business Understanding | Why are we doing this? | Anchor the portal to Reconnect, Re-engage, Re-hire and Self-serve; scope confirmed at G1 (end S2).
2 | Data Understanding | Do we have usable data? | Alumni profile data, directory fields, content library, privacy and consent; re-baselined at G-RB (end S2).
3 | Modeling | Can we build it? | Design system, 8 core screens and prototype in S0, then Build Pack waves W0-W5 across S1-S7, with gated options at G-AI, G-CH and G-CF.
4 | Evaluation | Does it work well enough? | Usability test with 5 alumni (FR-34), load test, WCAG 2.2 AA audit, security test and full UAT across S8-S12; signed at G4 and G5.
5 | Deployment | Will people actually use it? | PROD provision and release in S13, after the 18-check go-live gate 8.0.
6 | Monitoring | Is it still creating value? | Pilot with ~50 members and every staff role in S14, then two weeks of hypercare and handover in S15.
RACI key (RASCI)
Code | Role | Meaning
R | Responsible | Does the work. At least one per activity.
A | Accountable | Owns the outcome and the final decision. Exactly one per activity.
C | Consulted | Provides input before the work is finalised (two-way).
I | Informed | Kept up to date on progress or decisions (one-way).
S | Support | Assists or provides resources to the Responsible party (RASCI extension).
RAG status key
Code | Status | Meaning
G | Green | On track - no action required.
A | Amber | At risk - corrective action defined and being executed.
R | Red | Off track - escalation required to the Steering Committee.
RAID key
Code | Type | Meaning
R | Risk | A future event that may occur and would harm the project. Has probability and impact.
A | Assumption | Something taken as true without proof; must be validated or it becomes a risk.
I | Issue | A problem that has already occurred and needs resolution now.
D | Dependency | An external deliverable, decision or event the project relies on.

## Lifecycle Roadmap
CPMAI Lifecycle Roadmap - Oracle Alumni Network Portal
The CPMAI phases mapped to the 16 sprints S0-S15 and the 11 board gates. Each phase answers one question and must clear its exit criteria before the next begins.
Phase # | CPMAI Phase | Core Question | Objective | Key Activities | Key Deliverable / Gate | Exit Criteria | Duration (wks) | Accountable | Governance Touchpoint
0 | Setup & Mobilisation - S0 (19-30 Oct 2026) | Is the toolchain and team ready? | Stand up the toolchain, close the G0 blockers and confirm governance, funding and staffing. | Node, JDK 21 and SQLcl toolchain; dev ADB on APEX 26.1.5 (Q32); ADMIN bootstrap; OIDC client; workspace probe; secrets register; spike results. | G0 - Setup gate (end S0) | Toolchain validated; dev ADB and workspace OAN_APP ready; ADMIN bootstrap run; G0 open items closed. | 2 | PM / Delivery Lead | Steering Committee (S0 review)
1 | Business Understanding - S0 to S2 | Why are we doing this? | Anchor the portal to Reconnect, Re-engage, Re-hire and Self-serve, and sign off scope and acceptance criteria. | Content inventory and owner; scope and Must/Should/Could baseline; IA and navigation; privacy approach; traceability tagging. | G1 - Scope and AC sign-off (end S2) | Product owner signs off the Must/Should/Could AC list; content owner named. | 4-6 | Product Owner | Steering Committee + Privacy & Compliance Board
2 | Data Understanding - S1 to S2 | Do we have usable data? | Land the database baseline, confirm data sources and privacy, then re-baseline velocity. | DDL across identity, profile, chapters, content and ops; personal-data registry; seed reference data; audit and visibility; directory index; utPLSQL suites. | G-RB - Re-baseline (end S2) | Measured S1-S2 velocity and offline-rework actuals compared to plan; descope lane invoked if < 20 pd per sprint. | 4 | Data / Privacy Officer | Privacy & Compliance Board + PMO stand-up
3 | Modeling - S1 to S7 (Build Pack waves W0-W5) | Can we build it? | Build the design system and interface in Build Pack wave order with Build Pack page numbers (Q31). | W0 auth and admin; W1 shell and Home; W2 profile, directory, CV and work profile; W3 content and events; W4 messaging and channels; W5 jobs, helpdesk and organisations. | G-AI (end S3), G-CH (end S6), G-CF (end S7) | Each gated option passes its DPIA annex and external agreement before it is switched on in PROD. | 10-12 | UX Lead / Solution Architect | Design Authority + Compliance Board
4 | Evaluation - S8 to S12 | Does it work well enough? | Prove usability, accessibility, security, performance and compliance against targets. | Build packs W5-W7; 100k directory smoke test and full load test on temporary ADB; security test (ZAP); WCAG 2.2 AA audit; J-01..J-21 regression; UAT by role. | G2 (end S8), G3 (end S10), G4 and G5 (end S12) | Region decided and load-test ADB booked; staff roles named with 2-step verification; compliance complete; final UAT signed. | 10 | QA Lead / Product Owner | Steering Committee (go / no-go)
5 | Deployment - S13 (19-30 Apr 2027) | Will people actually use it? | Provision PROD, rehearse the deploy and go live against the 18-check gate. | Provision PROD and rehearsed deploy; seed chapters and attested admins; load legal texts; go-live checklist, rollback and smoke test. | 8.0 - Go-live gate (S13) | All 18 checks pass: DPIA per option, secrets, ORDS exposure and every Must acceptance criterion. | 2 | Delivery / Engineering Lead | Steering Committee + Brand Review Board
6 | Monitoring - S14 and S15 (and beyond) | Is it still creating value? | Pilot with real members, then hypercare, handover and value tracking. | Pilot with ~50 members, every staff role and >= 3 partner organisations; two weeks of hypercare; handover and v1.x backlog; KPI baseline plan. | Pilot (S14); hypercare and handover (S15) | Pilot validated; exit review kicked off; KPI baseline plan issued for go-live plus 3 months. | 4 + ongoing | Product Owner | Steering Committee (quarterly value review)
Responsible AI gate applies at every phase: Is it Legal? Ethical? Secure? Explainable? Valuable? Without trust there is no scale.

## Setup & Design Plan
Setup & Design Plan - S0 (19-30 Oct 2026) and S1 (2-13 Nov 2026)
Built from the delivery board: the 24 S0 setup tasks (toolchain, spikes, migrations) and the 20 S1 database-baseline tasks. Working days only; 'x' marks the planned working days. S0 closes gate G0; S1 delivers the first shared database deploy and feeds G1 and G-RB.
Board task detail (S0 + S1) | [9 empty] | S0 ¦ 19-30 Oct 2026 | S0 ¦ 19-30 Oct 2026 | S0 ¦ 19-30 Oct 2026 | S0 ¦ 19-30 Oct 2026 | S0 ¦ 19-30 Oct 2026 | S0 ¦ 19-30 Oct 2026 | S0 ¦ 19-30 Oct 2026 | S0 ¦ 19-30 Oct 2026 | S0 ¦ 19-30 Oct 2026 | S0 ¦ 19-30 Oct 2026 | S1 ¦ 2-13 Nov 2026 | S1 ¦ 2-13 Nov 2026 | S1 ¦ 2-13 Nov 2026 | S1 ¦ 2-13 Nov 2026 | S1 ¦ 2-13 Nov 2026 | S1 ¦ 2-13 Nov 2026 | S1 ¦ 2-13 Nov 2026 | S1 ¦ 2-13 Nov 2026 | S1 ¦ 2-13 Nov 2026 | S1 ¦ 2-13 Nov 2026
ID | Sprint | Category | Activity | Owner (R) | Accountable (A) | Dev pd | Priority | Status | Gate | Mon 19 Oct | Tue 20 Oct | Wed 21 Oct | Thu 22 Oct | Fri 23 Oct | Mon 26 Oct | Tue 27 Oct | Wed 28 Oct | Thu 29 Oct | Fri 30 Oct | Mon 02 Nov | Tue 03 Nov | Wed 04 Nov | Thu 05 Nov | Fri 06 Nov | Mon 09 Nov | Tue 10 Nov | Wed 11 Nov | Thu 12 Nov | Fri 13 Nov
0.1 | S0 | Environment | Node, JDK 21, SQLcl 26.2 installed | Solution Architect | Solution Architect | 0.5 | P0 | Done | G0 | x
0.5 | S0 | Environment | Git repo, layout, .gitignore | Solution Architect | Solution Architect | 0.25 | P0 | Done | G0 | x
0.4 | S0 | Environment | Workspace probe, deployment files, SQLcl connections | Solution Architect | Solution Architect | 0.5 | P0 | Done | G0 | x | x
0.2 | S0 | Environment | Dev ADB (APEX 26.1.5, Q32), synthetic data | Solution Architect | Solution Architect | 0.5 | P0 | Done | G0 | x | x | x
0.3 | S0 | Environment | ADMIN bootstrap: schemas, grants, OAN_CTX, sign-in hosts | Solution Architect | Solution Architect | 1.0 | P0 | Done | G0 |  | x | x | x
0.10 | S0 | Environment | Spike: APEX version on dev and PROD | Solution Architect | Solution Architect | 0.25 | P0 | Done | G0 |  | x
0.15 | S0 | Environment | Secrets register (all secrets, owners, rotation) | Solution Architect | Solution Architect | 1.0 | P0 | In progress | G0 |  | x | x
0.9 | S0 | Environment | CI: base-table scan, authz, utPLSQL, gitleaks, validate, page registry, brand | Solution Architect | Solution Architect | 2.5 | P0 | In progress | G0 |  |  | x | x | x | x
0.8 | S0 | Environment | utPLSQL on dev | Solution Architect | Solution Architect | 0.25 | P0 | Done | G0 |  |  |  | x | x
0.16a | S0 | Environment | Liquibase changelog (forward-only) | Solution Architect | Solution Architect | 1.5 | P0 | Not started | G0 |  |  |  | x | x | x
0.7 | S0 | Environment | OCI Email Delivery + APEX SMTP | Solution Architect | Solution Architect | 0.5 | P0 | Not started | G0 | [5 empty] | x | x
0.16b | S0 | Environment | Deploy wrapper + live validate gate | Solution Architect | Solution Architect | 0.75 | P0 | Done | G0 | [5 empty] | x | x
0.16c | S0 | Environment | Scratch-schema rebuild each sprint | Solution Architect | Solution Architect | 0.5 | P0 | Not started | G0 | [6 empty] | x | x
0.1b | S0 | Environment | Local Oracle DB Free + utPLSQL (optional) | Solution Architect | Solution Architect | 1.0 | P4 | Not started | G0 | [8 empty] | x | x
0.18 | S0 | Environment | Spike: APEX GenAI service | Solution Architect | Solution Architect | 0.5 | P4 | Not started | G0 | [8 empty] | x
0.19 | S0 | Environment | Procure Slack app, WhatsApp Business | Solution Architect | Solution Architect | OAN | P4 | Not started | G0 |  |  |  |  | x | x | x | x | x | x
0.6 | S0 | Environment | Google OIDC client | Solution Architect | Solution Architect | 0.5 | P0 | Blocked | G0 |  |  | x | x
0.11 | S0 | Environment | Spike: two-schema calls incl. ORDS | Solution Architect | Solution Architect | 1.0 | P0 | Done | G0 |  |  |  |  | x | x
0.12 | S0 | Environment | Spike: social sign-in, switch in session, re-auth | Solution Architect | Solution Architect | 1.0 | P0 | Blocked | G0 |  |  |  |  | x | x
0.13 | S0 | Environment | Spike: PBKDF2 210k under load | Solution Architect | Solution Architect | 0.5 | P0 | Done | G0 | [6 empty] | x
0.14 | S0 | Environment | Spike: Oracle Text on ADB | Solution Architect | Solution Architect | 0.5 | P0 | Done | G0 | [6 empty] | x
0.17 | S0 | Environment | Spike: webhook HMAC + async job < 1s | Solution Architect | Solution Architect | 1.5 | P4 | Blocked | G0 | [7 empty] | x | x
M.2 | S0 | Migration | Groups refactor: forums -> groups / posts / comments | Solution Architect | Solution Architect | 3.5 | P1 | Authored offline (validated, not live) | G0 | [7 empty] | x | x | x
M.1 | S0 | Migration | APEXLang 26.1 -> 26.2 metadata | Solution Architect | Solution Architect | 1.5 | P0 | Not started | G0 | [8 empty] | x | x
1.1-1.5 | S1 | Database | DDL: identity, profile, chapters, content, ops | Solution Architect | Solution Architect | 7.25 | P0 | Done | G1 / G-RB | [10 empty] | x | x
1.6 | S1 | Database | Personal-data registry + test | Solution Architect | Solution Architect | 0.75 | P0 | Done | G1 / G-RB | [11 empty] | x
1.7 | S1 | Database | Seed reference data | Solution Architect | Solution Architect | 2.0 | P0 | Done | G1 / G-RB | [11 empty] | x | x
1.8-1.13 | S1 | Database | Audit, context, visibility macro, views, security, auth packages | Solution Architect | Solution Architect | 10.75 | P0 | Done | G1 / G-RB | [10 empty] | x | x | x
1.14-1.22 | S1 | Database | Registration, profile, taxonomy, library, files, groups, moderation, notify, privacy | Solution Architect | Solution Architect | 15.0 | P0 | Done | G1 / G-RB | [12 empty] | x | x | x
1.23 | S1 | Database | Jobs package (fix failure link -> 1075) | Solution Architect | Solution Architect | 1.5 | P0 | In progress | G1 / G-RB | [13 empty] | x
1.24 | S1 | Database | Text/search split (search_body, directory index) | Solution Architect | Solution Architect | 2.0 | P1 | Done | G1 / G-RB | [13 empty] | x | x
1.25 | S1 | Database | Grants from manifest, synonyms, no-table-grant assert | Solution Architect | Solution Architect | 0.5 | P0 | Done | G1 / G-RB | [14 empty] | x
1.26 | S1 | Database | utPLSQL suites (R01, R16, R19/20, R26, secrets) | Solution Architect | Solution Architect | 4.0 | P0 | In progress | G1 / G-RB | [14 empty] | x | x
1.27 | S1 | Database | Throttle package | Solution Architect | Solution Architect | 1.0 | P0 | Done | G1 / G-RB | [15 empty] | x
1.29 | S1 | Database | Traceability + Must/Should/Could AC tags (feeds G1) | Solution Architect | Product Owner | 1.5 | P0 | Not started | G1 | [15 empty] | x | x
1.30 | S1 | Database | OAN_CTX: ORG/CHANNEL viewer, ROLES, in_group | Solution Architect | Solution Architect | 1.5 | P0 | Done | G1 / G-RB | [16 empty] | x
1.31 | S1 | Database | Staff scopes + single authz + one grant API | Solution Architect | Solution Architect | 1.5 | P0 | Done | G1 / G-RB | [16 empty] | x | x
1.28 | S1 | Database | Synthetic data: 100k profiles, 1M posts, 20k jobs | Solution Architect | Solution Architect | 2.5 | P0 | In progress | G1 / G-RB | [16 empty] | x | x
1.32 | S1 | Database | OAN_LU_CODE intents with live_yn (J01-J21 + roles) | Solution Architect | Product Owner | 0.5 | P1 | Authored offline (validated, not live) | G1 | [17 empty] | x
1.33 | S1 | Database | Retention rules + injectable clock | Solution Architect | Solution Architect | 1.0 | P0 | Done | G1 / G-RB | [17 empty] | x
1.34 | S1 | Database | Automations map, DBMS_LOCK run locks, send state machine | Solution Architect | Solution Architect | 1.5 | P0 | Done | G1 / G-RB | [18 empty] | x
1.35 | S1 | Database | Messaging permission, referral opt-in, directory switch | Solution Architect | Product Owner | 0.5 | P1 | Done | G1 / G-RB | [18 empty] | x
1.36 | S1 | Database | oan_export_pkg (person-level exports) | Solution Architect | Solution Architect | 1.0 | P0 | Done | G1 / G-RB | [18 empty] | x | x
1.37 | S1 | Database | option_live(): Build Option + DPIA sign-off | Solution Architect | Product Owner | 0.75 | P0 | Done | G1 / G-RB | [19 empty] | x
- S0 runs 19-30 Oct 2026 (10 working days) and closes gate G0; S1 runs 2-13 Nov 2026 and delivers the first shared database deploy (db-baseline-v1), feeding G1 and the G-RB re-baseline.
- Board totals: S0 = 21 tracked tasks, 18.75 pd; S1 = 17 tracked tasks, 49.25 pd. Estimates are developer person-days before the 20% contingency.
- Three S0 cards are Blocked on G0 decisions: 0.6 Google OIDC client, 0.12 social sign-in (Google sign-in set aside, Q33) and the staffing decision. 11 of 24 S0 cards are already Done and 15 of 20 S1 cards are Done, so the offline-authored database work is landing ahead of the sprint plan.
- Tiers P0-P4 come from docs/05-flow-priority.md: P0 and P1 are never cut; the S11 descope lane cuts from P4 upward.
- Day shading shows the planned working days within the S0-S1 window; exact daily scheduling is agreed at sprint planning.

## CXO Governance
CXO Governance - Tracking and Decision Rights
Who decides what, how often, and how it escalates. Governance is where AI initiatives are steered, not just reported.
Governance bodies
Governance Body | Purpose / Decision Rights | Chair | Members (Roles) | Cadence | Inputs | Outputs / Decisions | Escalation Path | Status
Executive Steering Committee (CXO) | Owns the business outcome. Approves charter, funding, v1 scope, design sign-off and go/no-go to build. | Executive Sponsor (CXO) | CXO sponsor, Product Owner, PM, Brand, HR/Talent, Marketing, Finance, Legal | Bi-weekly (weekly during gates) | Status report, KPI dashboard, RAID highlights, gate pack | Charter, budget, scope and gate decisions, escalations resolved | To Board / CEO for enterprise-level decisions | Active
Design Authority / Brand Review Board | Protects Oracle brand and design-system integrity across all 8 screens and components. | Brand Review Lead | Design Systems Lead, UX Lead, Marketing, Brand | Weekly during Modeling | Functional Specification v1.1, tokens, component library, screen designs | Brand and design approvals, standards | To Steering Committee | Active
Privacy & Compliance Board | Owns alumni PII, consent, directory visibility and data-protection compliance. | Privacy Officer | Legal, Security, Data Steward, Product Owner | At each gate + on demand | Privacy screen, data model, consent model | Consent and privacy approvals | To Steering Committee if a release is blocked | Active
Accessibility & Quality Board | Ensures WCAG 2.2 AA across breakpoints and a quality bar for the delivered experience. | Accessibility Lead | UX, QA, Front-end Lead, Brand | Bi-weekly | Accessibility spec, audit findings, QA results | Accessibility pass, quality decisions | To Steering Committee | Active
Product / Content Council | Prioritises screens, content and the roadmap; validates adoption and value. | Product Owner | UX Lead, Content Strategist, Marketing, Business, HR | Weekly | Roadmap, backlog, content plan, adoption metrics | Prioritised backlog, content decisions | To Steering Committee | Active
Architecture & Data Council | Approves the technical architecture, integrations, data contracts and the design-token export. | Solution Architect | Front-end Lead, Back-end Lead, Data Steward, Security | Bi-weekly + on demand | Architecture decisions, data model, integration map | Architecture and data approvals | To Steering Committee | Active
Delivery / PMO Stand-up | Runs day-to-day delivery, tracks the plan, RAID and dependencies. | Project Manager | Workstream leads, UX, Engineering, QA, Content | Daily / weekly | Plan, RAID, burndown, blockers | Delivery status, blocker resolution | To Steering Committee / Product Council | Active
CXO decision log
Decision ID | Date | Decision | Decided By | Rationale | Impact | Status
D-001 | [date] | Approve project charter and funding | Executive Steering Committee | Goals and measures of success agreed | Project mobilised | Approved
D-002 | [date] | Confirm v1 scope - 8 screens, admin/CMS and native apps out of scope | Steering Committee + Product Council | Functional Specification v1.1 scope | Scope baselined | Approved
D-003 | [date] | Approve directory-visibility default (opt-in vs opt-out) | Privacy & Compliance Board | Alumni privacy and consent | Consent model fixed | Pending
D-004 | [date] | Oracle Sans web licence for the alumni domain | Steering Committee | Brand typeface vs. open fallback | Typeface for build fixed | Pending
D-005 | [date] | Event registration in-portal vs. email | Product Council | Reference uses email; portal can register | Events scope fixed | Pending
D-006 | [date] | Gate 4 design sign-off / go to build | Executive Steering Committee | Usability and accessibility results vs. targets | Build authorised | Pending
D-007 | 2026-10-13 | Approve Plan V3.2: 16 sprints S0-S15, 11 gates, merged FSD scope built in Build Pack wave order | Executive Steering Committee | Delivery board baseline, iteration 9 | Delivery sequence baselined | Approved
D-008 | 2026-10-13 | Q31: build in APEX Build Pack wave order using Build Pack page numbers | Product Council | Keeps the build sequence aligned to the pack | Page numbering and build order fixed | Approved
D-009 | 2026-10-13 | Q32: dev runs APEX 26.1.5 (accepted); PROD APEX version policy remains open | Solution Architect / Steering | Dev ADB aiatp accepted on 26.1.5 | M.1 APEXLang 26.1 to 26.2 migration deferred on dev | Approved (dev)
D-010 | 2026-10-13 | Q29: no Oracle HR brokering - HR documents are signposted only | Privacy & Compliance Board | Avoids HR data processing in the portal | Helpdesk scope reduced to signposting | Approved
D-011 | 2026-10-13 | Q30: no Oracle logos on the portal | Brand Review Board | Brand governance | Brand expression limited to palette, type and layout | Approved
D-012 | 2026-10-13 | PROD region selection | Executive Steering Committee | Required before the temporary 100k load-test ADB can be booked | G2 (end S8) depends on this decision | Pending
Escalation path
Level 1 - Project Manager resolves within the delivery team (48 hours).
Level 2 - AI Product Owner / Product Council resolves cross-team issues (weekly).
Level 3 - Steering Committee resolves scope, budget, risk and gate decisions (bi-weekly).
Level 4 - Executive Sponsor / Board resolves enterprise-level or cross-portfolio decisions (as required).

## Change & Adoption
Change Management & Adoption Plan - Oracle Alumni Network Portal
Change is not an afterthought - readiness is built from week 1. ADKAR-based: Awareness > Desire > Knowledge > Ability > Reinforcement.
A. Change strategy
Case for change |  | Alumni currently reconnect and request documents through fragmented email and third-party sites. The portal gives them one authenticated home - reducing support effort and re-opening the talent pipeline.
Vision |  | Every Oracle alumnus has a single, trusted place to reconnect, re-engage, return and self-serve.
Change principles |  | Alumni-first; opt-in and privacy-respecting; gradual habit change over forced migration; champions lead peers; measure readiness, not just go-live.
Approach |  | ADKAR-based readiness (Awareness > Desire > Knowledge > Ability > Reinforcement) with comms, training, champions and reinforcement from week 1, not after launch.
What success looks like |  | Alumni choose the portal voluntarily: sign up, complete profiles, return monthly, message peers, register for events and self-serve documents.
B. Stakeholder analysis
Stakeholder / Group | Type | Interest | Influence | Current State | Desired State | Engagement Approach | Owner
Alumni (all members) | End user | High | Medium | Unaware | Aware and active | Launch comms, portal, social, reminders | Change & Comms Lead
Alumni champions (per region) | Advocate | High | High | Unaware | Engaged and advocating | 1:1 briefing, champion toolkit, community | Change & Comms Lead
HR / Talent | Beneficiary | High | High | Supportive | Embedded (boomerang pipeline) | Joint workshops, process update | HR / Talent Lead
Marketing / Communications | Delivery partner | High | Medium | Supportive | Co-delivering launch | Joint comms plan, content cadence | Marketing Lead
Support / Helpdesk | Impacted team | High | Medium | Neutral | Trained and confident | Training, FAQs, operational readiness | Support Lead
Brand / Design Authority | Gatekeeper | Medium | High | Supportive | Approved and aligned | Reviews at each gate | Brand Review Lead
Legal / Privacy | Gatekeeper | Medium | High | Cautious | Compliant and assured | Review packs, consent model sign-off | Privacy Officer
IT / Security | Enabler | Medium | High | Supportive | Aligned | Architecture and security reviews | Solution Architect
CXO / Steering Committee | Sponsor | Medium | High | Supportive | Active sponsor | Steering cadence, value reviews | Executive Sponsor
C. Change impact assessment
Area | Who Is Impacted | What Changes | Impact Level | Mitigation / Enablement | Owner
Onboarding & sign-up | All alumni | Registration and identity verification replace informal access | Medium | Clear comms, one-step verified sign-up, support FAQ | Change & Comms Lead
Profile completion | All alumni | Alumni must add role history and current details | Medium | Completion meter, nudges, smart defaults, explain the value | Product Owner
Directory visibility | All alumni | New privacy setting controls who can find them | High | Explicit consent, safe default, plain-language explanation | Privacy Officer
Engagement habit | All alumni | Return visits replace one-off contact | High | Content cadence, notifications, event programme, champions | Marketing Lead
Document requests | Alumni + Support | Email back-and-forth becomes self-serve form | Medium | Comms, training, in-portal guidance, support fallback | Support Lead
Support operations | Helpdesk team | New tooling, new request types, new SLAs | Medium | Training, runbook, hypercare | Support Lead
Talent pipeline | HR / Talent | Boomerang applications arrive via the portal | Medium | Process update, briefing, referral tracking | HR / Talent Lead
Comms channel | Marketing | A new always-on alumni channel to feed | Low | Briefing, content calendar, ownership agreed | Marketing Lead
D. Communication plan
Audience | Key Message | Channel | Owner | Timing | Frequency
Invited alumni | The portal is live - reconnect with your Oracle network | Email, social, portal | Change & Comms Lead | Week 4 / launch | Once + 2 reminders
Registered alumni | What's new - insights, events and your network | In-portal feed, email | Content Strategist | From launch | Weekly
Alumni champions | Champion programme briefing and toolkit | 1:1 / community call | Change & Comms Lead | Week 3 | Monthly
HR / Talent | Boomerang pipeline now runs through the portal | Email + workshop | HR / Talent Lead | Week 3 | Once
Support / Helpdesk | Operational readiness and new request handling | Training + runbook | Support Lead | Week 4 | Once
CXO / Steering Committee | Adoption and value progress | Steering pack | Product Owner | Bi-weekly | Recurring
Legal / Privacy | Compliance and consent status | Review pack | Privacy Officer | At each gate | Per gate
Wider Oracle staff | Support our alumni - share the portal | Intranet | Change & Comms Lead | Launch | Once
E. Training & enablement plan
Audience | What They Learn | Format | Owner | Timing | Completion Target
All alumni | Sign up, complete profile, find people, message, events | Job aid + short video | Change & Comms Lead | Week 4 to launch | 100% reach
Alumni champions | Champion toolkit, talking points, how to help peers | Workshop | Change & Comms Lead | Week 3 | 100% of champions
Support / Helpdesk | Request handling, FAQs, escalation paths | Instructor-led training | Support Lead | Week 4 | 100% of agents
HR / Talent | Careers and boomerang process in the portal | Briefing | HR / Talent Lead | Week 3 | 100% of team
Content team | Publishing, moderation and the content calendar | Workshop | Content Strategist | Week 4 | 100% of team
Administrators | Admin / CMS console - deferred from v1 | n/a (out of scope v1) | Product Owner | Post v1 | Deferred
F. ADKAR readiness tracker
ADKAR Element | What It Means Here | Key Actions | Readiness Measure | Owner | Status
A - Awareness | Alumni understand why the portal exists and what it offers | Launch comms, leadership letter, social | Comms reach / awareness | Change & Comms Lead | Not started
D - Desire | Alumni want to join and take part | Champions, peer stories, clear value | Sign-up intent survey | Change & Comms Lead | Not started
K - Knowledge | Alumni know how to use the portal | Training assets, job aids, onboarding | Training reach | Change & Comms Lead | Not started
A - Ability | Alumni can complete key tasks unaided | Usability fixes, empty states, support | Usability task success | UX Lead | Not started
R - Reinforcement | New habits and value are sustained after launch | Content cadence, notifications, value reports | Monthly return visits | Marketing Lead | Not started
G. Change KPIs (also on the KPI Dashboard)
KPI ID | KPI | Definition / Formula | Baseline | Target | Owner | Frequency
CK-01 | Change readiness score | avg ADKAR readiness across audiences | [baseline] | >= 80% | Change & Comms Lead | Weekly from week 3
CK-02 | Comms reach / awareness | alumni who saw launch comms / invited | 0% | >= 80% | Change & Comms Lead | Launch + 2 weeks
CK-03 | Training completion | target audience trained / total target | 0% | >= 90% | Change & Comms Lead | By launch
CK-04 | Champion coverage | regions or teams with an active champion / total | 0% | >= 80% | Change & Comms Lead | Week 4
CK-05 | Resistance / escalations | count of open high change-resistance items | [baseline] | 0 high | Change & Comms Lead | Weekly

## Success Plan
Success Plan - Definition of Success, Adoption and Benefits
AI success = Business + Data + Technology + Adoption. Success is defined, measured and owned before build begins.
A. Value hypothesis
Problem / opportunity |  | [Describe the business problem or opportunity in one sentence.]
Proposed agentic solution |  | [Describe the agent, the workflow it automates and where a human stays in the loop.]
Expected outcome |  | [Describe the measurable business outcome and the value it creates.]
Why agentic AI |  | [Explain why an autonomous agent - not a simpler automation - is the right fit.]
Value at stake |  | [Quantify the annual value at stake, e.g. cost, revenue, risk, experience.]
B. Success criteria
ID | Success Criterion | Category | Metric | Baseline | Target | Measurement Method | Owner | Timeframe
SC-01 | Alumni locate and follow a former colleague quickly | Reconnect | Searches to find a colleague | [baseline] | Within 2 searches | Usability test + search analytics | UX Lead | Gate 4 / post-launch
SC-02 | Alumni return to the portal regularly | Re-engage | Monthly return visits | [baseline] | [target] by month 3 | Web analytics | Product Owner | Month 3 post go-live
SC-03 | Alumni apply to return to Oracle | Re-hire | Boomerang applications via Careers | [baseline] | [target] per quarter | Careers referral tracking | HR / Talent Lead | Quarterly
SC-04 | Document requests are resolved without email back-and-forth | Self-serve | Self-serve resolution rate | [baseline] | >= 70% | Helpdesk request logs | Support Lead | Month 2 post go-live
SC-05 | The portal is usable by real alumni | Usability | Task success rate in usability test | [baseline] | >= 85% | Usability test with 5 alumni | UX Research Lead | Gate 4
SC-06 | The portal is accessible | Accessibility | WCAG 2.2 AA conformance | Not assessed | AA pass, 0 critical | Accessibility audit | Accessibility Lead | Gate 4
SC-07 | The portal is on-brand | Brand | Brand review outcome | n/a | Pass, 0 critical | Design Authority review | Brand Review Lead | Gate 4
SC-08 | Design is ready for build | Delivery | Screens signed off + tokens exported | 0 | 8 of 8 + token export | Handoff checklist | Design Systems Lead | Gate 4
SC-09 | Profiles are complete enough to be useful | Adoption | Average profile completion | 69% (reference) | >= 90% | Profile completion meter | Product Owner | Month 2 post go-live
SC-10 | The board delivers on the gate sequence | Delivery | Gates passed on or before their due date | 0 of 11 | 11 of 11 by S13 | Gate Checklist | Product Owner | S13 (go-live)
SC-11 | Effort stays within the estimate and contingency | Delivery | pd delivered vs the 319.75 pd plan incl. 20% contingency | 0 | Within +/- 10% of plan | Board Tasks + Sprint Performance Tracker | PM | S13 (go-live)
C. Adoption plan
Element | Audience | Action | Owner | Timing | Success Signal
Executive sponsorship | CXO / Steering Committee | Visible sponsorship, gate decisions, value review | Executive Sponsor | Ongoing | Gates attended, decisions made
Alumni communication plan | All alumni | Launch comms, what's new feed, email and social | Change & Comms Lead | From Gate 4 | Awareness and sign-up rate
Profile completion nudges | Registered alumni | In-app completion meter nudges to 100% | Product Owner | From launch | Avg completion >= 90%
Onboarding & first-run | New members | Guided first-run and empty-state guidance | UX Lead | From launch | First-session task completion
Champion network | Alumni leaders / regions | Peer advocacy and event promotion | Change & Comms Lead | From launch | Champions active per region
Content cadence | All members | Regular insights, perspectives and announcements | Content Strategist | Weekly from launch | Return visits driven by content
Events programme | All members | In-portal registration and calendar for events | Marketing Lead | From launch | Registrations per event
Feedback loop | All members | In-app feedback and support routed to the backlog | Product Owner | From launch | Feedback triaged weekly
Value storytelling | CXO + organisation | Publish realised value and lessons | Product Owner | Monthly | Value report issued
Pilot programme | ~50 members, every staff role, >= 3 partner organisations | Run the S14 pilot across all staff roles and partner orgs before hypercare | Product Owner | S14 (3-14 May 2027) | Pilot validated; exit review kicked off
Hypercare and handover | Support, HR, Marketing, Operations | Two weeks of hypercare, then handover and the v1.x backlog | Delivery Lead | S15 (17-28 May 2027) | Handover complete; backlog agreed
D. Benefits realisation
Benefit ID | Benefit | Type | Quantified Value | Baseline | Realisation Date | Owner | Status
B-01 | Reduced support effort for document requests (self-serve) | Cost / productivity | [value] | [baseline] | [date] | Support Lead | Planned
B-02 | Reconnect: alumni network activity and relationships re-established | Engagement | [value] | [baseline] | [date] | Product Owner | Planned
B-03 | Re-engage: increased monthly return visits and content reach | Engagement | [value] | [baseline] | [date] | Marketing Lead | Planned
B-04 | Re-hire: boomerang talent pipeline via Careers | Talent | [value] | [baseline] | [date] | HR / Talent Lead | Planned
B-05 | Reusable Oracle-branded design system for future alumni and talent portals | Strategic | [value] | [baseline] | [date] | Design Systems Lead | Planned
E. Definition of Done
- The agent performs the target task end-to-end at or above the agreed quality threshold.
- Responsible AI controls are in place and approved; audit trail is complete.
- Users are trained, enabled and actively adopting the agent in the real workflow.
- KPIs meet their targets at Gate 4 and continue to hold at the Gate 6 value review.
- Benefits are validated against the baseline and reported to the Steering Committee.

## Value Stream Map
Value Stream Map - As-Is Alumni Engagement Flow
Map the flow from trigger to value. Find the stages where wait time and rework destroy value - that is where agentic AI earns its place.
As-is value stream
Stage # | Stage Name | Entry Trigger | Key Activities | VA / NVA | Lead Time (days) | Process Time (days) | Wait Time (days) | Flow Efficiency | Pain Points | Systems / Data | Opportunity | Target State | Priority
1 | Discover & sign up | An alumnus hears about the portal | Learn about the portal, register, verify identity | NVA | 3.0 | 0.3 | 2.7 | 10% | Unclear invitation, verification friction, no single entry point | Email, marketing, SSO | Clear invitation and one-step verified sign-up | Frictionless, verified onboarding | High
2 | Complete profile | Signed up | Add role history, location, current role, photo | VA | 14.0 | 1.0 | 13.0 | 7% | Long form, unclear value, profile stalls at 69% | Profile service | Completion meter, nudges and smart defaults | >= 90% profile completion | High
3 | Find former colleagues | Wants to reconnect | Search and filter the alumni directory | VA | 2.0 | 0.3 | 1.7 | 15% | Weak filters, poor data, dead ends | Directory, profile data | Strong filters (tenure, line of business, last role) and relevant results | Find within 2 searches | High
4 | Connect & converse | Found a colleague | Follow, message, join groups | VA | 1.0 | 0.3 | 0.7 | 30% | No messaging in the old experience; email back-and-forth | Conversations service | In-portal 1:1 and group messaging with announcements | In-portal conversation | High
5 | Engage with insights & events | Portal visit | Read insights, register for events | VA | 2.0 | 0.5 | 1.5 | 25% | Content scattered, event sign-up by email | Content, events | Curated feed and in-portal event registration + calendar | Self-serve engagement | High
6 | Explore return-to-Oracle | Considering a return | Search Oracle and partner jobs; boomerang programme | VA | 5.0 | 0.5 | 4.5 | 10% | Careers opens a separate site; unclear path back | Careers, HR | Embedded boomerang hero and in-portal job search | Boomerang applications grow | Medium
7 | Request HR documents | Needs a document | Request payslips, Form-16, relieving letter | VA | 6.0 | 0.3 | 5.7 | 5% | Email back-and-forth, no status, manual handling | Helpdesk, HR | Self-serve request form with consent and reference ID | Resolved without email | High
8 | Re-engage & return | Time passes | Return visits driven by content, events, network | NVA | 30.0 | 0.5 | 29.5 | 2% | No reason to return; no habit loop | Analytics, content | Regular content cadence, notifications and event programme | Monthly return visits grow | High
Flow summary
Metric | As-Is | Target (To-Be) | Improvement
Total lead time (days) | 63.0 | [target] | [x]
Total process time (days) | 3.7 | [target] | [x]
Total wait time (days) | 59.3 | [target] | [x]
Flow efficiency (process / lead) | 6% | >= 25% | +19 pts
Stages with high-value opportunity | 6 of 8 | 6 of 8 | -
Highest-leverage stages | 2, 3, 4, 7 (Profile, Find, Connect, Self-serve) | Target these first | -
Flow efficiency = process time / lead time. Low efficiency means the work waits more than it works - the prime target for an autonomous agent.

## KPI Dashboard
KPI Dashboard - Measuring What Matters
Business, adoption, data, technology, Responsible AI and delivery KPIs - each with a definition, baseline, target, owner and RAG threshold. Delivery KPIs (cards complete, gate pass rate, effort burn, blocked cards, descope use) are read from the Kanban Dashboard.
KPI ID | Category | KPI | Definition / Formula | Data Source | Frequency | Baseline | Target | Green / Amber / Red | Owner | Linked Criterion | Current Value | RAG
K-01 | Reconnect | Searches to find a colleague | avg searches before a successful follow | Analytics | Weekly | [baseline] | <= 2 | G <=2 / A 3 / R >3 | UX Lead | SC-01
K-02 | Reconnect | Directory search success rate | searches returning a result / total searches | Analytics | Weekly | [baseline] | >= 90% | G >=90 / A 75-89 / R <75 | Product Owner | SC-01
K-03 | Reconnect | Follow / connect rate | members followed / directory visitors | Analytics | Weekly | [baseline] | >= 25% | G >=25 / A 12-24 / R <12 | Product Owner | SC-01
K-04 | Re-engage | Monthly return visits | distinct members returning in a month | Analytics | Monthly | [baseline] | [target] by month 3 | G >=target / A 70-99% / R <70% | Marketing Lead | SC-02
K-05 | Re-engage | Content engagement rate | article reads / active members | Analytics | Monthly | [baseline] | >= 40% | G >=40 / A 20-39 / R <20 | Content Strategist | SC-02
K-06 | Re-engage | Event registrations per event | registrations per published event | Events service | Per event | [baseline] | [target] | G >=target / A 70-99% / R <70% | Marketing Lead | SC-02
K-07 | Re-hire | Boomerang applications | applications via Careers per quarter | Careers / HR | Quarterly | [baseline] | [target] | G >=target / A 70-99% / R <70% | HR / Talent Lead | SC-03
K-08 | Re-hire | Careers engagement | job searches and role views in-portal | Analytics | Monthly | [baseline] | [target] | G >=target / A 70-99% / R <70% | HR / Talent Lead | SC-03
K-09 | Self-serve | Self-serve resolution rate | requests resolved without email / total | Helpdesk logs | Weekly | [baseline] | >= 70% | G >=70 / A 45-69 / R <45 | Support Lead | SC-04
K-10 | Self-serve | Document request turnaround | avg hours from request to resolution | Helpdesk logs | Weekly | [baseline] | <= 48h | G <=48 / A 49-96 / R >96 | Support Lead | SC-04
K-11 | Self-serve | Form completion rate | requests submitted / forms started | Helpdesk logs | Weekly | [baseline] | >= 85% | G >=85 / A 65-84 / R <65 | UX Lead | SC-04
K-12 | Adoption | Registered alumni | verified members / invited alumni | Auth / analytics | Monthly | [baseline] | [target] | G >=target / A 70-99% / R <70% | Change & Comms Lead | SC-02
K-13 | Adoption | Average profile completion | avg completion % across members | Profile service | Weekly | 69% (reference) | >= 90% | G >=90 / A 75-89 / R <75 | Product Owner | SC-09
K-14 | Adoption | Messaging activity | messages sent / active members | Conversations | Weekly | [baseline] | [target] | G >=target / A 70-99% / R <70% | Product Owner | SC-02
K-15 | Quality | Usability task success | tasks completed unaided / tasks set | Usability test | Gate 4 | [baseline] | >= 85% | G >=85 / A 70-84 / R <70 | UX Research Lead | SC-05
K-16 | Quality | WCAG 2.2 AA conformance | AA success criteria passed / total | Accessibility audit | Gate 4 + ongoing | Not assessed | 100% AA, 0 critical | G 100 / A 95-99 / R <95 | Accessibility Lead | SC-06
K-17 | Quality | Brand review outcome | brand issues found at review | Design Authority | Gate 4 | n/a | 0 critical | G 0 / A 1-2 minor / R any critical | Brand Review Lead | SC-07
K-18 | Quality | Page load performance | LCP at p75 on desktop | RUM / monitoring | Weekly | [baseline] | <= 2.5s | G <=2.5 / A 2.6-4 / R >4 | Front-end Lead | SC-05
K-19 | Privacy | Consent coverage | members with valid consent / registered | Consent service | Monthly | [baseline] | 100% | G 100 / A 95-99 / R <95 | Privacy Officer | SC-06
K-20 | Privacy | Privacy incidents | count of PII / privacy incidents | Monitoring | Continuous | 0 | 0 | G 0 / R >0 | Privacy Officer | SC-06
K-21 | Delivery | Screens signed off | screens approved / 8 | PMO | Weekly | 0 | 8 of 8 | G 8 / A 6-7 / R <6 | Product Owner | SC-08
K-22 | Delivery | Spec review-gate pass rate | specs approved first time / submitted | PMO | Per feature | [baseline] | >= 80% | G >=80 / A 60-79 / R <60 | Product Owner | SC-08
K-23 | Delivery | Schedule adherence | milestones met on time / total | PMO | Bi-weekly | [baseline] | >= 90% | G >=90 / A 75-89 / R <75 | Project Manager | SC-08
K-24 | Delivery | RAID open high items | count of open high/critical RAID items | RAID log | Weekly | [baseline] | 0 overdue high | G 0 / A 1-2 / R >2 | Project Manager | SC-08
K-25 | Change & Adoption | Change readiness score | avg ADKAR readiness across audiences | Readiness survey | Weekly from week 3 | [baseline] | >= 80% | G >=80 / A 60-79 / R <60 | Change & Comms Lead | SC-02
K-26 | Change & Adoption | Comms reach / awareness | alumni reached by launch comms / invited | Comms analytics | Launch + 2 wks | 0% | >= 80% | G >=80 / A 60-79 / R <60 | Change & Comms Lead | SC-02
K-27 | Change & Adoption | Training completion | target audience trained / total target | Training records | By launch | 0% | >= 90% | G >=90 / A 70-89 / R <70 | Change & Comms Lead | SC-04
K-28 | Change & Adoption | Champion coverage | regions / teams with an active champion | Champion register | Week 4 | 0% | >= 80% | G >=80 / A 50-79 / R <50 | Change & Comms Lead | SC-02
K-29 | Change & Adoption | Resistance / escalations | open high change-resistance items | Change log | Weekly | [baseline] | 0 high | G 0 / A 1-2 / R >2 | Change & Comms Lead | SC-02
K-30 | Delivery | Sprint velocity | delivered story points per sprint | Performance Tracker | Per sprint | [baseline] | [target] | G >=target / A 80-99% / R <80% | Scrum Master | SC-08
K-31 | Delivery | Sprint commitment reliability | delivered SP / committed SP | Performance Tracker | Per sprint | [baseline] | 0.90 - 1.10 | G 0.90-1.10 / A 0.80-0.89 or 1.11-1.20 / R outside | Scrum Master | SC-08
K-32 | Delivery | Capacity utilisation | delivered SP / team capacity SP | Performance Tracker | Per sprint | [baseline] | 75 - 90% | G 75-90 / A 60-74 / R <60 | Scrum Master | SC-08
K-33 | Delivery | Spill-over points | story points carried into the next sprint | Capacity Planner | Per sprint | [baseline] | <= 10% of commitment | G <=10% / A 11-20% / R >20% | Scrum Master | SC-08
K-34 | CV & Work Profile | CV currency | members with a CV updated or confirmed in the last 6 months / total | Profile service | Monthly | [baseline] | >= 80% | G >=80 / A 60-79 / R <60 | Product Owner | SC-09
K-35 | CV & Work Profile | Work profile currency | members with a work profile confirmed in the last 6 months / total | Profile service | Monthly | [baseline] | >= 85% | G >=85 / A 65-84 / R <65 | Product Owner | SC-09
K-36 | CV & Work Profile | Update request completion | requests closed on update / requests raised | Update queue | Monthly | [baseline] | >= 70% | G >=70 / A 45-69 / R <45 | Product Owner | SC-09
K-37 | Channel | Channel-linked members | members with a linked Slack or WhatsApp identity / registered | Channel identities | Monthly | 0% | [target] | G >=target / A 70-99% / R <70% | Integration / Channel Lead | SC-02
K-38 | Channel | Channel message resolution | inbound channel messages resolved with an intent / total | Channel messages | Weekly | [baseline] | >= 90% | G >=90 / A 75-89 / R <75 | Integration / Channel Lead | SC-02
K-39 | Channel | Channel delivery success | channel messages delivered / queued | Channel messages | Weekly | [baseline] | >= 98% | G >=98 / A 95-97 / R <95 | Integration / Channel Lead | SC-02
K-40 | Channel | Opt-in compliance | outbound WhatsApp sent without opt-in | Channel messages | Continuous | 0 | 0 | G 0 / R >0 | Privacy Officer | SC-06
K-41 | Delivery | Cards complete on the board | cards in Done or Authored offline / 154 tracked | Delivery Board | Weekly | 70 of 154 (iteration 23) | >= 90% by end S13 | G >=90 / A 70-89 / R <70 | Scrum Master / Delivery Lead | SC-10
K-42 | Delivery | Gate pass rate | gates passed on time / gates due | Gate Checklist | Per gate | 0 of 11 | 100% on or before due date | G 100 / A 80-99 / R <80 | Product Owner | SC-10
K-43 | Delivery | Effort burn vs plan | cumulative pd delivered / 319.75 pd plan | Board Tasks | Weekly | 0% | Within +/- 10% of plan | G <=10 / A 11-20 / R >20 | PM | SC-11
K-44 | Delivery | Blocked cards | cards in Blocked status on the board | Delivery Board | Weekly | 3 | 0 by end S2 | G 0 / A 1-2 / R >2 | Delivery Lead | SC-10
K-45 | Delivery | Descope lane use | P4 pd cut at the S11 descope lane | Sprint Capacity Planner | At S11 | 0 pd | <= 10% of P4 pd | G <=10 / A 11-20 / R >20 | Product Owner | SC-11

## RACI Matrix
RACI Matrix - Oracle Alumni Network Portal
R = Responsible ¦ A = Accountable (exactly one) ¦ C = Consulted ¦ I = Informed ¦ S = Support
CPMAI Phase | Activity | Executive Sponsor (CXO) | Steering Committee | Product Owner | Project Manager | UX Lead | UI / Visual Designer | Design Systems Lead | Content Strategist | Front-end Lead | Back-end Lead | Solution Architect | Accessibility Lead | Data / Privacy Officer | Brand Review Lead | Change & Comms Lead | Scrum Master / Delivery Lead | Integration / Channel Lead
Mobilise | Approve project charter and funding | A | R | C | S | C |  | C |  |  |  | C |  | C | C
Mobilise | Stand up governance bodies | A | C | C | R | C |  | C | C |  |  | C | C | C | C | C
Mobilise | Agree RACI and ways of working | I | I | A | R | C | C | C | C | C | C | C | C | C | C | C
Business Understanding | Stakeholder review of Functional Specification v1.1 | I | I | R | S | C | C | C | C |  |  | C | C | C | C | C
Business Understanding | Confirm goals and measures of success | A | C | R | S | C |  |  | C |  |  |  |  | C |  | C
Business Understanding | Confirm v1 scope (8 screens, in / out) | A | C | R | S | C |  | C | C | C | C | C
Business Understanding | Validate IA and navigation model | I | I | A | S | R | C | C | C | C |  | C | C
Business Understanding | Content inventory and copy rules | I | I | A | S | C | C |  | R | [5 empty] | C | C
Business Understanding | Privacy and consent screening | I: A; I: C; A: C; S: S |  | C |  | R
Business Understanding | Confirm governance cadence | I: A; I: C; A: C; S: R; R: C |  |  |  | C | C | C
Data Understanding | Define alumni data model and directory fields | I | I | C | S | C |  |  | C | C | C | A |  | R
Data Understanding | Confirm data sources and integrations | I: I; I: C; A: C; S: S; C: C | R | A |  | C
Data Understanding | Agree directory-visibility defaults | I: A; I: C; A: C; S: S |  | C | C | R
Data Understanding | Resolve open questions (licence, letter, events, regions) | A | C | R | S |  |  | C | C |  |  | C |  | C | C | C
Data Understanding | Finalise design tokens | I | I | C | S | C | C | R |  | C |  | C | C |  | A
Data Understanding | Accessibility spec - WCAG 2.2 AA | I | C | C | S | C | C | C |  | C |  | C | R |  | A
Data Understanding | Responsive breakpoint spec | I | I | C | S | R | C | C |  | C |  | C | C |  | A
Data Understanding | Content and copy rules; data fallbacks | I | I | A | S | C | C |  | R | [5 empty] | C | C
Modeling | Shape and write screen specs | I | I | A | S | R | C | C | C | C | C | C | C
Modeling | Build component library | I | I | C | S | C | C | R | C | C |  |  | C |  | A
Modeling | Design the 8 core screens | I | I | A | S | C | R | C | C |  |  |  | C |  | C
Modeling | Build clickable hi-fi prototype | I | I | A | S | R | C | C |  |  |  |  | C
Modeling | Accessibility review of the prototype | I | C | C | S | C | C | C |  | C |  |  | R |  | A
Evaluation | Usability test with 5 alumni | I | I | A | S | R | C |  | C |  |  |  | C |  |  | C
Evaluation | Analyse findings and prioritise fixes | I | I | A | S | R | C | C | C |  |  |  | C
Evaluation | WCAG 2.2 AA audit and remediation | I | C | C | S | C |  | C |  | R | C | C | A |  | C
Evaluation | Brand compliance and quality review | I | C | C | S | C | C | C | C |  |  |  | C |  | R
Evaluation | Stakeholder review and design sign-off | A | R | C | S | C |  | C | C | [5 empty] | C
Evaluation | Dev handoff and token export | I | I | C | S | C | C | R |  | C | C | C | C
Evaluation | Go / No-Go decision to build | A | R | C | S | C |  | C |  | C | C | C | C | C | C | C
Deployment | Front-end and back-end build | I | C | C | S | C | C | C |  | R | R | C | C
Deployment | Integration, QA and launch | I | C | A | R | C |  | C |  | R | R | C | C | C |  | C
Deployment | Alumni onboarding and launch comms | I | I | A | S | C |  |  | C |  |  |  |  | C |  | R
Monitoring | Monitor adoption, engagement and quality | I | C | A | S | C |  | C | C | C | C | C | C | C |  | C
Monitoring | Track benefits realisation and value | A | C | R | S | C |  |  | C |  |  |  |  | C |  | C
Monitoring | Run continuous improvement backlog | I | I | A | S | C | C | C | C | C | C | C | C | C |  | C
Business Understanding | Change impact assessment | I: I; I: C; A: A; S: S; C: C; C: C; C: C | C | R
Business Understanding | Stakeholder analysis and engagement map | I: I; I: C; A: A; S: S; C: C; C: C | C | R
Business Understanding | Change strategy and case for change | I: A; I: C; A: R; S: S; C: C; C: C | C | R
Data Understanding | Communication plan and launch narrative | I: I; I: C; A: A; S: S; C: C; C: C | C | R
Data Understanding | Training needs analysis | I: I; I: I; A: A; S: S; C: C; C: C | C | R
Data Understanding | Adoption readiness baseline survey | I: I; I: I; A: A; S: S; C: C; C: C | C | R
Modeling | Develop training and enablement assets | I: I; I: I; A: A; S: S; C: C; C: C; C: C | C | R
Modeling | Champion network setup | I: I; I: I; A: A; S: S; C: C; C: C | C | R
Modeling | Change readiness check and resistance plan | I: A; I: C; A: C; S: S; C: C; C: C | C | R
Evaluation | Finalise launch comms and onboarding pack | I: I; I: C; A: A; S: S; C: C; C: C | C | R
Evaluation | Adoption measurement plan and post-launch cadence | I: I; I: C; A: A; S: S; C: C; C: C | C | R
Delivery | Sprint planning and capacity management | I | I | A | C | C | C | C | C | C | C | C | C |  |  | C | R
Delivery | Sprint review, demo and retrospective | I | C | A | S | C | C | C | C | C | C | C | C |  |  | C | R
Delivery | Sprint performance tracking and velocity forecast | I: I; C: C; A: A; S: C |  |  |  | R
Business Understanding | Define CV structure and work profile fields | I | I | A | S | C | C | C |  |  |  | C |  |  | C | C
Data Understanding | Agree CV review cadence and update policy | I: A; C: C; A: R; S: S; C: C; C: C; C: C | C |  | C
Modeling | Design CV builder and work profile screens | I | I | A | S | R | C | C | C |  |  |  | C |  | C
Evaluation | Validate CV builder and profile update flow | I | I | A | S | R | C |  | C |  |  |  | C |  |  | C
Business Understanding | Confirm Slack and WhatsApp channel scope | A | C | R | S | C |  | C |  |  | C | C |  | C |  | C | R
Data Understanding | Channel identity model and opt-in policy | A | C | C | S |  |  | C |  |  | C | C |  | R |  | C | R
Modeling | Spec inbound and outbound channel handling | I | C | C | S |  |  | C |  | C | C | R | C | C |  |  | A
Evaluation | Channel end-to-end and security test | I | C | A | S |  |  | C |  | C | C | C | C | C |  |  | R
S0 | Toolchain, spikes and migrations - close G0 | I: R; I: A; A: C
S1-S2 | Database baseline, W0 auth and admin - G1 and G-RB | I: R; I: A; A: C; S: I
S3-S7 | Build packs W0-W5 including gated options - G-AI, G-CH, G-CF | I: R; I: A; A: I
S8-S11 | Build packs W5-W7 and the descope lane - G2 and G3 | I: R; I: A; A: C
S12-S13 | Hardening, UAT and go-live - G4, G5 and gate 8.0 | I: R; I: A; A: C; S: I
S14-S15 | Pilot with ~50 members, hypercare and handover | I: R; I: A; A: I

## RAID Log
RAID Log - Risks, Assumptions, Issues, Dependencies
Living register aligned to the delivery board: G0 blockers, gated build options and the descope lane. Reviewed weekly at the PMO stand-up; high items escalate to the Steering Committee.
Register
ID | Type | Description | Category | Probability / Impact | Score | Owner | Mitigation / Response | Due Date | Status
R-001 | Risk | Oracle Sans web licence for the alumni domain is not secured in time | Brand | Medium / High | 12 | Brand Review Lead | Confirm licence or proceed on the Albert Sans fallback; decide at Gate 2. | [date] | Open
R-002 | Risk | Leadership letter author and portrait approval delays the Home hero | Content | Medium / High | 12 | Content Strategist | Start approval early; use a placeholder slide until sign-off. | [date] | Open
R-003 | Risk | Alumni profile data is incomplete or contains raw null / N-A values | Data | High / Medium | 12 | Data / Privacy Officer | Data quality assessment; enforce graceful fallbacks ('-', 'Open to opportunities'). | [date] | Open
R-004 | Risk | Directory-visibility default (opt-in vs opt-out) is unresolved and blocks the directory | Privacy | Medium / High | 12 | Privacy Officer | Decide at the Privacy & Compliance Board in week 2; document the consent model. | [date] | Open
R-005 | Risk | Scope creep beyond v1 (admin / CMS console, native apps, analytics dashboards) | Scope | High / Medium | 12 | Product Owner | Baselined out-of-scope list; change control via Steering Committee. | [date] | Open
R-006 | Risk | Accessibility (WCAG 2.2 AA) gaps found late in the build | Compliance | Medium / High | 12 | Accessibility Lead | Accessibility spec in week 2; prototype review in week 3; audit in week 4. | [date] | Open
R-007 | Risk | Low alumni adoption after launch | Adoption | Medium / High | 12 | Change & Comms Lead | Launch comms, content cadence, champions, profile nudges; track return visits weekly. | [date] | Open
R-008 | Risk | Reference-portal patterns leak through instead of Oracle brand | Brand | Medium / Medium | 9 | Brand Review Lead | Design Authority review at each gate; brand substitution table applied globally. | [date] | Open
R-009 | Risk | Integration with Oracle Careers / events / HR is harder than expected | Technical | Medium / Medium | 9 | Solution Architect | Confirm integration map in week 2; define deep-link fallbacks. | [date] | Open
A-001 | Assumption | Alumni data and directory fields are available for the build | Data | Medium / High | 12 | Data / Privacy Officer | Confirm availability in Data Understanding; escalate gaps. | [date] | Open
A-002 | Assumption | SSO / verified-email authentication is available for the alumni domain | Technical | Medium / High | 12 | Solution Architect | Confirm auth approach in week 2. | [date] | Open
A-003 | Assumption | Reference screenshots remain available to guide structure | Design | Low / Medium | 6 | UX Lead | Archive reference material; capture in the design document. | [date] | Open
A-004 | Assumption | Oracle brand assets and imagery are available from the brand library | Brand | Medium / Medium | 9 | Brand Review Lead | Request brand assets in week 2; use placeholders until supplied. | [date] | Open
A-005 | Assumption | CXO sponsorship and funding remain stable | Governance | Low / High | 9 | Executive Sponsor | Regular value reporting; visible quick wins; steering engagement. | [date] | Open
I-001 | Issue | Open questions in the design document are unresolved (licence, letter, registration, regions, privacy default) | Scope | n/a / High | High | Product Owner | Resolve in weeks 1-2 via the decision log; escalate to Steering if unresolved. | [date] | Open
D-001 | Dependency | Oracle Sans web licence decision | Brand | Medium / High | 12 | Brand Review Lead | Confirm in week 2; fallback is Albert Sans. | [date] | Open
D-002 | Dependency | Leadership letter author and portrait approval | Content | Medium / High | 12 | Content Strategist | Track with the content owner; placeholder until approved. | [date] | Open
D-003 | Dependency | SSO provider / verified-email setup | Technical | Medium / High | 12 | Solution Architect | Confirm approach in week 2; needed for build. | [date] | Open
D-004 | Dependency | Oracle Careers deep-link and partner marketplace integration | Technical | Medium / Medium | 9 | Solution Architect | Confirm deep-link contract before Deployment. | [date] | Open
D-005 | Dependency | Legal / privacy sign-off on consent and terms | Compliance | Medium / High | 12 | Privacy Officer | Submit in week 2; sign-off before Gate 4. | [date] | Open
D-006 | Dependency | Alumni participants for the usability test (6-8) | Resource | Medium / Medium | 9 | UX Research Lead | Recruit and confirm before Gate 3. | [date] | Open
R-010 | Risk | Alumni resist sharing profile data or distrust the privacy default | Adoption | High / Medium | 12 | Change & Comms Lead | Explicit consent, safe default, plain-language comms, privacy FAQ. | [date] | Open
R-011 | Risk | Habit change fails - alumni keep emailing for documents instead of self-serving | Adoption | Medium / High | 12 | Support Lead | Comms + training, in-portal guidance, phased email redirection, track self-serve rate. | [date] | Open
A-006 | Assumption | Alumni are willing to self-serve rather than rely on email | Adoption | Medium / Medium | 9 | Change & Comms Lead | Validate via the readiness baseline survey in week 2. | [date] | Open
D-007 | Dependency | Alumni champions nominated per region | Change | Medium / High | 12 | Change & Comms Lead | Confirm champions by week 3 to support launch. | [date] | Open
R-012 | Risk | Sprint capacity is overstated (allocation, ramp-up or ceremonies under-estimated) | Delivery | Medium / High | 12 | Scrum Master | Use the risk-adjusted velocity and planning buffer; reconcile against actuals every sprint. | [date] | Open
A-007 | Assumption | The build team is available at the planned allocation across all sprints | Resource | Medium / Medium | 9 | Scrum Master | Confirm allocations before Sprint 1; track capacity utilisation. | [date] | Open
R-013 | Risk | CVs and work profiles go stale, so partners and peers stop trusting the directory | Adoption | High / Medium | 12 | Product Owner | Cadence-driven update requests, reminders on enabled channels, currency KPIs K-34/K-35. | [date] | Open
R-014 | Risk | WhatsApp opt-in or template approval is not secured in time | Compliance | Medium / High | 12 | Privacy Officer | Start Business verification early; ship Slack first; keep WhatsApp feature-flagged off. | [date] | Open
R-015 | Risk | Channel secrets or webhook endpoints are misconfigured or exposed | Security | Low / High | 9 | Security Architect | Secrets stored as references only; signature verification; replay log; security test in H.7. | [date] | Open
R-016 | Risk | Slack app approval is delayed by the workspace owner | Dependency | Medium / Medium | 9 | Integration / Channel Lead | Raise the app request in week 1; confirm scope H.1 early. | [date] | Open
D-008 | Dependency | Slack workspace owner approval for the OAN app | Integration | Medium / High | 12 | Integration / Channel Lead | Confirm in week 1-2. | [date] | Open
D-009 | Dependency | WhatsApp Business account verification and approved templates | Integration | Medium / High | 12 | Integration / Channel Lead | Start verification early; templates approved before go-live. | [date] | Open
D-010 | Dependency | Secrets store available for channel credentials | Security | Medium / High | 12 | Security Architect | Confirm with IT in week 2. | [date] | Open
R-017 | Risk | Six cards are blocked on G0 (ADMIN bootstrap, Google OIDC client, staffing decision), holding up S1-S2 database and auth work | Schedule / Resource | High / High | H | Delivery Lead | Close the G0 items first and run the offline-authored database work in parallel so S1 starts unblocked | End S0 | Open
R-018 | Risk | The descope lane triggers if measured velocity falls below 20 pd per sprint | Delivery | Medium / High | M | Product Owner | G-RB re-baselines after S2 and invokes the S11 descope lane, cutting from P4 upward | End S2 (G-RB) | Open
R-019 | Risk | PROD APEX version policy is unresolved (dev runs 26.1.5 under Q32) and could force late rework | Technical | Medium / Medium | M | Solution Architect | Close the PROD version policy before S13; keep M.1 (APEXLang metadata migration) in scope | S12 | Open
R-020 | Risk | Gated build options (AI assistant, channels, Careers feed) slip if their DPIA annexes and external DPAs are not signed | Compliance | High / High | H | Compliance Officer | Gate each option on its own annex: G-AI (end S3), G-CH (end S6), G-CF (end S7) | Per gate | Open
R-021 | Risk | Slack app, WhatsApp Business app and the Meta/Slack DPAs sit on the critical path for the channel build in S7 | Delivery | Medium / High | M | Integration / Channel Lead | Procure both apps and start the DPAs during S0-S3 so S7 has verified accounts | S6 (G-CH) | Open
R-022 | Risk | The 20% contingency may be insufficient if rework grows after the S14 pilot | Cost | Medium / Medium | M | PM | Track actuals every sprint on the Sprint Performance Tracker and re-baseline at G-RB | S14 | Open
D-011 | Dependency | ADMIN run of the bootstrap to create schemas, grants, OAN_CTX and sign-in hosts (G0) | Environment | High / High | H | DBA / ADMIN | Script is ready; needs an ADMIN account run to complete | End S0 | Open
D-012 | Dependency | Google OIDC client credentials to be provided by OAN (G0) | Access | High / High | H | OAN IT | OAN to provide the client; blocks the social sign-in spikes (0.12) | End S0 | Open
D-013 | Dependency | OAN-owned compliance deliverables: DPIAs, DPAs, legal texts and the grievance officer | Compliance | High / High | H | OAN Compliance | OAN-owned; gates G-AI, G-CH, G-CF and G4 | Per gate | Open
D-014 | Dependency | Temporary 100k load-test ADB to be booked for the full load test (G2) | Infrastructure | Medium / High | M | Solution Architect | Book before S8; used for the full load test in S9 | S8 (G2) | Open
Scoring and status key
Probability |  | High = >60% likely ¦ Medium = 20-60% ¦ Low = <20%
Impact |  | High = major (cost, schedule, brand, compliance) ¦ Medium = moderate ¦ Low = minor
Score |  | Probability x Impact (High=3, Medium=2, Low=1); 6-9 = high priority, 3-5 = medium, 1-2 = low
Status |  | Open ¦ In Progress ¦ Mitigated ¦ Closed ¦ Escalated
Review |  | Reviewed weekly at PMO stand-up; high items reported to Steering Committee.

## Artefact Register
Artefact Register - Plan Aligned to Deliverables
Every programme artefact, its version, its owner and the plan workstream that produces it. This is how the plan stays aligned with the artefacts.
Artefact ID | Artefact | Type | Version | Owner | Plan Workstream | Governing FRs | Status
A-01 | Functional Specification (FSD) | Document | 1.1 | Product Owner | Business Understanding | FR-01 to FR-24 | Draft for review
A-02 | Database schema (Oracle DDL) | SQL | 1.1 | AI Architect | Data Understanding | Data model for all FRs | Ready for build
A-03 | Data dictionary | Spreadsheet | 1.1 | Data Steward | Data Understanding | Data model for all FRs | Ready for build
A-04 | Entity relationship diagram | Diagram | 1.1 | AI Architect | Data Understanding | Data model for all FRs | Ready for build
A-05 | OAN_CHAT_API package | PL/SQL | 1.1 | Integration / Channel Lead | Modeling | FR-01, FR-17, FR-23, FR-24 | Skeleton delivered
A-06 | OAN_NOTIFY_API package | PL/SQL | 1.1 | Integration / Channel Lead | Modeling | FR-16, FR-23, FR-24 | Skeleton delivered
A-07 | APEX Application Build Pack | Document | 1.1 | Scrum Master / Delivery Lead | Modeling | All FRs (build order) | Draft for review
A-08 | APEX Build Tracker | Spreadsheet | 1.1 | Scrum Master / Delivery Lead | Delivery | All FRs (page inventory) | In use
A-09 | CXO Build Plan and Build Order deck | Presentation | 1.0 | Product Owner | Governance | All FRs (executive view) | For steering review
A-10 | Project Plan (CPMAI) | Spreadsheet | 1.1 | Project Manager | Governance | All FRs (delivery) | Draft for review
A-11 | Sprint Capacity Planner | Spreadsheet | 1.0 | Scrum Master / Delivery Lead | Delivery | Delivery capacity | In use
A-12 | RAID Log | Spreadsheet | 1.1 | Project Manager | Governance | Delivery risk | Live
A-13 | Change & Adoption Plan | Spreadsheet | 1.1 | Change & Comms Lead | Change & Adoption | Adoption outcomes | Live
A-14 | OAN Portal Delivery Board (16 sprints, 11 gates, 154 tasks) | Board | V3.2 / it. 9 | PMO / Delivery Lead | Delivery control | All 24 FRs (J-01..J-21) | Baseline 13 Oct 2026
A-15 | Gate Checklist (G0-G5, G-AI, G-CH, G-CF, G-RB, 8.0) | Register | V3.2 | Product Owner | Governance | Compliance and release gates | Live
A-16 | Kanban Board (154 tracked cards by status) | Board | V3.2 | Scrum Master / Delivery Lead | Delivery control | All 24 FRs | Live
A-17 | Kanban Dashboard (flow, effort and priority metrics) | Dashboard | V3.2 | Scrum Master / Delivery Lead | Delivery control | Delivery KPIs | Live
A-18 | Board Tasks register (id, task, category, pd, tier, status) | Register | V3.2 | Scrum Master / Delivery Lead | Delivery control | All 24 FRs | Live
A-19 | Sprint Planner Dashboard (capacity and performance charts) | Dashboard | V3.2 | PMO / Delivery Lead | Capacity management | Delivery KPIs | Live
A-20 | Sprint Roadmap (16 sprints S0-S15 and 11 gates) | Plan | V3.2 | Scrum Master / Delivery Lead | Capacity management | All 24 FRs | Live
Alignment rules
- A change to any artefact updates its version here and re-runs the affected workstream tasks.
- The Functional Specification governs every other artefact; the schema, packages and build pack must trace to it.
- The build pack and build tracker are regenerated whenever a page, grid or API routine changes.
- The CXO deck is refreshed from the build pack before every steering review.
- The project plan, RAID log and capacity planner are updated weekly and at every gate.

## Sprint Capacity Planner
Sprint Capacity Planner - Oracle Alumni Network Portal
Plans one sprint at a time. Pale-yellow cells are editable inputs; white cells calculate automatically.
Activity | Product Owner | Scrum Master / Delivery Lead | UX Lead | UI / Visual Designer | Design Systems / Front-end | Back-end Engineer | Solution Architect | Accessibility / QA Lead | Content Strategist | Change & Comms Lead | Total | SPRINT & ASSUMPTIONS
Sprint Planning | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 40 | Sprint Number | S1 (Build)
Backlog Grooming / Tasking | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 40 | Sprint Start Date | 2026-11-02
Daily Stand-up | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 25 | Sprint End Date | 2026-11-13
Sprint Retrospective | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 15 | Hours per Working Day | 8
Sprint Review | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 15 | Sprint Planning (hrs/person) | 4
Sprint Demo | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 10 | Backlog Grooming (hrs/person) | 4
Sub-total: Repeating Ceremonies | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 145 | Daily Standup (min/day) | 15
Adhoc Meetings | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 25 | Sprint Retrospective (hrs) | 1.5
Sub-total: Non-Scrum Meetings | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 25 | Sprint Review (hrs) | 1.5
Total Meeting Load | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 170 | Sprint Demo (hrs) | 1
Resource Allocation % | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0.5 | 1 | 0.5 | 0.5 | Team | Adhoc Meetings buffer (hrs/person) | 2.5
Total Available Time | 40 | 40 | 80 | 80 | 80 | 80 | 40 | 80 | 40 | 40 | 600 | Holidays in this Sprint (days) | 0
Vacation / Leave (hrs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Avg Hours per Story Point | 8
Public Holiday (hrs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Planning Risk Buffer % | 10%
Actual Available Hours | 23 | 23 | 63 | 63 | 63 | 63 | 23 | 63 | 23 | 23 | 430 | Sprint Working Days (auto) | 10
Maturity / Ramp-up Level | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Factor | Total Sprint Hours per FTE (auto) | 80
Hours Available for Sprint | 23 | 23 | 63 | 63 | 63 | 63 | 23 | 63 | 23 | 23 | 430
Story-Point Capacity | 2.875 | 2.875 | 7.875 | 7.875 | 7.875 | 7.875 | 2.875 | 7.875 | 2.875 | 2.875 | 53.75
Expected Team Velocity (SP) | 53.75
Risk-Adjusted Velocity (after buffer) | 48.375
Spill-Over Points from Previous Sprint | 0
Recommended Sprint Commitment (SP) | 48.375
Final Committed SP (team decision) | 0
Legend
Pale yellow = editable input ¦ White = calculated by formula
Sprint Working Days is calculated with NETWORKDAYS from the sprint start and end dates, less holidays.
Story-Point Capacity = Hours Available for Sprint / Avg Hours per Story Point.
Recommended Sprint Commitment = Risk-Adjusted Velocity - Spill-Over Points. The team agrees the final number.

## Sprint Performance Tracker
Sprint Performance Tracker - Oracle Alumni Network Portal
Logs every closed sprint. Completion, utilisation, 3-sprint trend and next-sprint forecast are calculated.
Rows below are an ILLUSTRATIVE BASELINE carried from the attached planner - replace with your actual sprint data.
Sprint | Start Date | End Date | Holidays (days) | Working Days | Team Capacity (SP) | Committed (SP) | Delivered (SP) | Completion % | Capacity Utilisation % | 3-Sprint Avg Delivered | Trend | Sprint Index
Sprint 1 | 2026-03-30 | 2026-04-10 | 0 | 10 | 34 | 32 | 27 | 84.38% | 79.41% | 27 | — | 1
Sprint 2 | 2026-04-13 | 2026-04-24 | 0 | 10 | 36 | 34 | 30 | 88.24% | 83.33% | 28.5 | ▲ Improving | 2
Sprint 3 | 2026-04-27 | 2026-05-08 | 0 | 10 | 33 | 30 | 25 | 83.33% | 75.76% | 27.3333 | ▼ Declining | 3
Sprint 4 | 2026-05-11 | 2026-05-22 | 1 | 9 | 38 | 36 | 33 | 91.67% | 86.84% | 29.3333 | ▲ Improving | 4
Sprint 5 | 2026-05-25 | 2026-06-05 | 0 | 10 | 35 | 33 | 29 | 87.88% | 82.86% | 29 | ▼ Declining | 5
Sprint 6 | 2026-06-08 | 2026-06-19 | 0 | 10 | 40 | 38 | 35 | 92.11% | 87.5% | 32.3333 | ▲ Improving | 6
Sprint 7 | 2026-06-22 | 2026-07-03 | 0 | 10 | 37 | 35 | 33 | 94.29% | 89.19% | 32.3333 | ▬ Stable | 7
Sprint 8 | 2026-07-06 | 2026-07-17 | 0 | 10 | 42 | 40 | 37 | 92.5% | 88.1% | 35 | ▲ Improving | 8
Sprint 9 | 2026-07-20 | 2026-07-31 | 1 | 9 | 39 | 37 | 35 | 94.59% | 89.74% | 35 | ▬ Stable | 9
Sprint 10 | 2026-08-03 | 2026-08-14 | 0 | 10 | 44 | 42 | 39 | 92.86% | 88.64% | 37 | ▲ Improving | 10
Sprint 11 | 2026-08-17 | 2026-08-28 | 0 | 10 | 41 | 39 | 37 | 94.87% | 90.24% | 37 | ▬ Stable | 11
Sprint 12 | 2026-08-31 | 2026-09-11 | 0 | 10 | 46 | 44 | 42 | 95.45% | 91.3% | 39.3333 | ▲ Improving | 12
Trend & forecast
Velocity trend (SP gained per sprint) |  |  | 1.2517
Next sprint forecast — delivered SP |  |  | 41.6364
Average completion rate (all sprints) |  |  | 91.01%
Average capacity utilisation (all sprints) |  |  | 86.08%
Live dashboard
Current sprint capacity (SP) |  |  | 53.75
Risk-adjusted capacity (SP) |  |  | 48.375
Recommended commitment (SP) |  |  | 48.375
Average completion rate |  |  | 86.08%
Next sprint forecast (SP) |  |  | 0.91013
Resource hours — current sprint (from the Capacity Planner)
Resource | Role | Hours Available | Story-Point Capacity | Allocation % | Maturity
Resource 1 | Product Owner | 23 | 2.875 | 0.5 | 1
Resource 2 | Scrum Master / Delivery Lead | 23 | 2.875 | 0.5 | 1
Resource 3 | UX Lead | 63 | 7.875 | 1 | 1
Resource 4 | UI / Visual Designer | 63 | 7.875 | 1 | 1
Resource 5 | Design Systems / Front-end | 63 | 7.875 | 1 | 1
Resource 6 | Back-end Engineer | 63 | 7.875 | 1 | 1
Resource 7 | Solution Architect | 23 | 2.875 | 0.5 | 1
Resource 8 | Accessibility / QA Lead | 63 | 7.875 | 1 | 1
Resource 9 | Content Strategist | 23 | 2.875 | 0.5 | 1
Resource 10 | Change & Comms Lead | 23 | 2.875 | 0.5 | 1
Formulas:
Working Days = NETWORKDAYS([Start Date],[End Date])-[Holidays (days)]

## Sprint Roadmap
Sprint Roadmap - 16 Sprints S0-S15 and the 11 Gates
Sprint sequence from the attached delivery board (Plan V3.2, iteration 9). Capacity per sprint is planned on the Sprint Capacity Planner.
Sprint | Sprint Window | CPMAI Phase | Focus / Screens | Key Deliverable | Exit / Gate
S0 | 19-30 Oct 2026 | Phase 1-4 (setup) | Toolchain, spikes, migrations; design system and 8 core screens continue in parallel | Toolchain ready, migrations validated | G0
S1 | 2-13 Nov 2026 | Phase 5 (Deployment) | First shared DB deploy - DDL, security, auth packages | db-baseline-v1 deployed
S2 | 16-27 Nov 2026 | Phase 5 (Deployment) | DB tests, W0 auth + admin pages | W0 pages and DB tests green | G1, G-RB
S3 | 30 Nov-11 Dec 2026 | Phase 5 (Deployment) | W0 onboarding, W1 shell | Onboarding and shell live in DEV | G-AI
S4 | 14-25 Dec 2026 | Phase 5 (Deployment) | W2 profile + directory tables and index | Profile and directory foundation
S5 | 28 Dec 2026-8 Jan 2027 | Phase 5 (Deployment) | W2 CV and privacy; product-owner demo 1 | My CV + current work profile (pages 24, 25)
S6 | 11-22 Jan 2027 | Phase 5 (Deployment) | W3 content, W4 messaging package | Content and messaging live | G-CH
S7 | 25 Jan-5 Feb 2027 | Phase 5 (Deployment) | W4 channels, W5 organisations | Slack + WhatsApp channels (page 43) | G-CF
S8 | 8-19 Feb 2027 | Phase 5 (Deployment) | W5 jobs, helpdesk, W6 experts; demo 2 | Jobs, helpdesk and expert network | G2
S9 | 22 Feb-5 Mar 2027 | Phase 5 (Deployment) | W6 groups, partner workspace, mentoring | Community and partner surface
S10 | 8-19 Mar 2027 | Phase 5 (Deployment) | W6 training, initiatives; demo 3; buffer | Training and initiatives | G3
S11 | 22 Mar-2 Apr 2027 | Phase 5 (Deployment) | W7 reports; descope lane active | Admin dashboard and analytics
S12 | 5-16 Apr 2027 | Phase 5 (Hardening) | Load, WCAG 2.2 AA, security, full UAT | Full AC regression and UAT sign-off | G4, G5
S13 | 19-30 Apr 2027 | Phase 5 (Release) | Gate 8.0 and PROD release | Production go-live | 8.0
S14 | 3-14 May 2027 | Phase 6 (Monitoring) | Pilot ~50 members, every staff role, >= 3 orgs | Pilot validated
S15 | 17-28 May 2027 | Phase 6 (Monitoring) | Hypercare (2 weeks) and handover | Handover + v1.x backlog
S0 is the setup sprint, with the design system and 8 core screens proceeding in parallel. Build sprints are 2 weeks, planned with velocity-based capacity and a planning-risk buffer. S11 carries the descope lane; S12-S15 cover hardening, go-live, pilot and hypercare.

## Board Tasks
Board Tasks - the 154 tracked cards behind the Kanban
One row per card on the attached delivery board. The Kanban Board and Kanban Dashboard read this sheet.
ID | Task | Category | Dev pd | Priority | Status
0.16a | Liquibase changelog (forward-only) | Environment | 1.5 | P0 | Not started
0.16c | Scratch-schema rebuild each sprint | Environment | 0.5 | P0 | Not started
0.18 | Spike: APEX GenAI service | Environment | 0.5 | P4 | Not started
0.19 | Procure Slack app, WhatsApp Business | Environment | OAN | P4 | Not started
0.1b | Local Oracle DB Free + utPLSQL (optional) | Environment | 1 | P4 | Not started
0.20 | ORDS install: OAN_API schema, channel modules | Environment | 1 | P4 | Not started
0.7 | OCI Email Delivery + APEX SMTP | Environment | 0.5 | P0 | Not started
1.29 | Traceability + Must/Should/Could AC tags | Database | 1.5 | P0 | Not started
5.1 | Full AC regression + evidence pack | Quality | 4 | P0 | Not started
5.10 | J-01..J-21 end-to-end regression | Quality | 3 | P0 | Not started
5.2 | Security test (ZAP, bypass, leaks) | Quality | 3 | P0 | Not started
5.3a | 100k directory smoke test | Quality | 1 | P1 | Not started
5.3b | Full load test on temporary ADB | Quality | 3 | P0 | Not started
5.3c | Load test re-run | Quality | 1 | P0 | Not started
5.4 | Full WCAG 2.2 AA audit | Quality | 2 | P0 | Not started
5.4a | First WCAG 2.2 pass | Quality | 0.5 | P1 | Not started
5.5 | Restore test, RPO/RTO | Quality | 0.5 | P0 | Not started
5.6 | OCI Health Checks | Quality | 0.5 | P0 | Not started
5.7 | Security and privacy test matrix | Quality | 8 | P0 | Not started
5.8 | Test identities per role and context | Quality | 1 | P0 | Not started
5.9 | FR-34 usability test (5 alumni) | Quality | 1 | P0 | Not started
6.3a | Synthetic content import rehearsal | Content & adoption | 0.5 | P0 | Not started
6.3b | Content import into PROD | Content & adoption | 1.5 | P0 | Not started
6.8 | >= 3 partner orgs verified for pilot | Content & adoption | OAN | P0 | Not started
7.1a | Core DPIA + RoPA (incl. antivirus risk) | Compliance | OAN | P0 | Not started
7.1b | DPIA annex: AI assistant | Compliance | OAN | P0 | Not started
7.1c | DPIA annex: channels | Compliance | OAN | P0 | Not started
7.1d | DPIA annex: Careers feed | Compliance | OAN | P0 | Not started
7.2a | DPAs: OCI, Google, LinkedIn, email | Compliance | OAN | P0 | Not started
7.2b | DPA: GenAI provider | Compliance | OAN | P0 | Not started
7.2c | DPAs: Slack, Meta | Compliance | OAN | P0 | Not started
7.3 | Legal texts incl. partner, channel, HR notices | Compliance | OAN | P0 | Not started
7.4 | Grievance officer, breach runbook | Compliance | OAN | P0 | Not started
7.5 | Owners, access policy, Q6 + EXPERT/TRAINER confirmation | Compliance | OAN | P0 | Not started
8.0 | Go-live gate (18 checks) | Release | 1.5 | P0 | Not started
8.1 | Provision PROD + rehearsed deploy | Release | 1 | P0 | Not started
8.2 | Seed chapters, assign attested admins | Release | 0.5 | P0 | Not started
8.3 | Pilot: ~50 members, every staff role, >= 3 orgs | Release | OAN | P0 | Not started
8.4 | Exit review kickoff | Release | OAN | P0 | Not started
8.5 | Load legal texts v1 | Release | 0.25 | P0 | Not started
8.7 | KPI baseline plan (go-live + 3 months) | Release | OAN | P0 | Not started
9.1 | UAT plan by role and journey | Acceptance | 1.5 | P0 | Not started
9.2 | Final UAT sign-off (G5) | Acceptance | 3 | P0 | Not started
9.2a | Product-owner demo: W0-W2 | Acceptance | 1 | P0 | Not started
9.2b | Product-owner demo: W3-W5 | Acceptance | 1 | P0 | Not started
9.2c | Product-owner demo: W6 | Acceptance | 1 | P0 | Not started
9.3-9.5 | Admin guide, member FAQ, runbook | Acceptance | 4.5 | P0 | Not started
9.6 | Go-live checklist, rollback, smoke test | Acceptance | 0.5 | P0 | Not started
9.7 | Hypercare (2 weeks) | Acceptance | 3 | P0 | Not started
9.8 | Handover + v1.x backlog | Acceptance | 1 | P0 | Not started
M.1 | APEXLang 26.1 -> 26.2 metadata | Migration | 1.5 | P0 | Not started
W0.16 | Terms versions, deny-list, breached passwords | W0 Auth & admin | 0.75 | P0 | Not started
W0.17 | Health pages | W0 Auth & admin | 0.25 | P0 | Not started
W0.20 | Build Option wiring + enable_feature | W0 Auth & admin | 1.5 | P0 | Not started
W6.2 | Experts + expert requests (Page 63, J-14) | W6 Community & partners | 4.5 | P3 | Not started
W6.3 | Mentoring + sessions (Page 65, J-05) | W6 Community & partners | 4 | P3 | Not started
W6.4 | Training, enrolment, mock projects (Page 67, J-06, J-13) | W6 Community & partners | 4.5 | P3 | Not started
W6.5 | Partner workspace: talent requests, feedback (Page 70, J-09..J-19) | W6 Community & partners | 6 | P3 | Not started
W6.6 | Chapters pages (Page 74) | W6 Community & partners | 1.5 | P3 | Not started
W6.7 | Marketplace (descope lane, Page 75, Could) | W6 Community & partners | 2 | P4 | Not started
W6.8 | Initiatives + success stories (Pages 77, 78, J-07) | W6 Community & partners | 6.25 | P3 | Not started
W6.9 | Recognition and badges (descope lane, Could) | W6 Community & partners | 3 | P4 | Not started
W7.1 | Admin dashboard with 6 goal KPIs (Page 100) | W7 Reporting | 2 | P2 | Not started
W7.2 | Reports & analytics, exports (Page 1085) | W7 Reporting | 4 | P2 | Not started
W7.3 | Config + job runs (Pages 122, 123) | W7 Reporting | 1.5 | P2 | Not started
0.15 | Secrets register (all secrets, owners, rotation) | Environment | 1 | P0 | In progress
0.9 | CI: base-table scan, authz, utPLSQL, gitleaks, validate, page registry, brand | Environment | 2.5 | P0 | In progress
1.23 | Jobs package (fix failure link -> 1075) | Database | 1.5 | P0 | In progress
1.26 | utPLSQL suites (R01, R16, R19/20, R26, secrets) | Database | 4 | P0 | In progress
1.28 | Synthetic data: 100k profiles, 1M posts, 20k jobs | Database | 2.5 | P0 | In progress
W0.15 | Audit log, report modal, my decisions | W0 Auth & admin | 2 | P0 | In progress
W0.18 | Shared components + security baseline | W0 Auth & admin | 7.5 | P0 | In progress
W2.10 | Profile update + privacy request admin (Page 121) | W2 Profile & directory | 2.5 | P0 | In progress
W2.9 | Account settings + privacy centre | W2 Profile & directory | 5 | P0 | In progress
W3.5 | Library moderation, import, events admin | W3 Content & events | 5 | P1 | In progress
W5.1 | Organisations: application, verification (Pages 55, 1025) | W5 Jobs & helpdesk | 4.5 | P2 | In progress
W5.7 | Careers deep-links (feed gated, G-CF) | W5 Jobs & helpdesk | 0.75 | P2 | In progress
W6.1 | Groups governance, reactions, stories, private search | W6 Community & partners | 5 | P1 | In progress
1.32 | OAN_LU_CODE intents with live_yn | Database | 0.5 | P1 | Authored offline (validated, not live)
M.2 | Groups refactor: forums -> groups / posts / comments | Migration | 3.5 | P1 | Authored offline (validated, not live)
W0.10 | Approval queue + application review | W0 Auth & admin | 2 | P0 | Authored offline (validated, not live)
W0.11 | Members, staff roles, scopes | W0 Auth & admin | 3 | P0 | Authored offline (validated, not live)
W0.12 | Chapters + chapter requests | W0 Auth & admin | 1.5 | P0 | Authored offline (validated, not live)
W0.13 | Lookups / taxonomy admin | W0 Auth & admin | 2 | P0 | Authored offline (validated, not live)
W0.14 | Moderation queue + appeals | W0 Auth & admin | 2.5 | P0 | Authored offline (validated, not live)
W0.21 | OAN_CHAT_API + OAN_NOTIFY_API (Build Pack contracts) | W0 Auth & admin | 2 | P0 | Authored offline (validated, not live)
W0.22 | Build Pack conventions: AI_ items, IS_* names, Build Pack options | W0 Auth & admin | 0.75 | P0 | Authored offline (validated, not live)
0.12 | Spike: social sign-in, switch in session, re-auth | Environment | 1 | P0 | Blocked
0.17 | Spike: webhook HMAC + async job < 1s | Environment | 1.5 | P4 | Blocked
0.6 | Google OIDC client | Environment | 0.5 | P0 | Blocked
W0.9 | AI assistant (read-only, opt-in) | W0 Auth & admin | 3 | P4 | Gated by Build Option
W4.4a | Slack channel | W4 Messaging & channels | 6 | P4 | Gated by Build Option
W4.4b | WhatsApp channel + channel settings (Page 43) | W4 Messaging & channels | 6 | P4 | Gated by Build Option
0.1 | Node, JDK 21, SQLcl 26.2 installed | Environment | 0.5 | P0 | Done
0.10 | Spike: APEX version on dev and PROD | Environment | 0.25 | P0 | Done
0.11 | Spike: two-schema calls incl. ORDS | Environment | 1 | P0 | Done
0.13 | Spike: PBKDF2 210k under load | Environment | 0.5 | P0 | Done
0.14 | Spike: Oracle Text on ADB | Environment | 0.5 | P0 | Done
0.16b | Deploy wrapper + live validate gate | Environment | 0.75 | P0 | Done
0.2 | Dev ADB (APEX 26.1.5, Q32), synthetic data | Environment | 0.5 | P0 | Done
0.3 | ADMIN bootstrap: schemas, grants, OAN_CTX, sign-in hosts | Environment | 1 | P0 | Done
0.4 | Workspace probe, deployment files, SQLcl connections | Environment | 0.5 | P0 | Done
0.5 | Git repo, layout, .gitignore | Environment | 0.25 | P0 | Done
0.8 | utPLSQL on dev | Environment | 0.25 | P0 | Done
1.1-1.5 | DDL: identity, profile, chapters, content, ops | Database | 7.25 | P0 | Done
1.14-1.22 | Registration, profile, taxonomy, library, files, groups, moderation, notify, privacy | Database | 15 | P0 | Done
1.24 | Text/search split (search_body, directory index) | Database | 2 | P1 | Done
1.25 | Grants from manifest, synonyms, no-table-grant assert | Database | 0.5 | P0 | Done
1.27 | Throttle package | Database | 1 | P0 | Done
1.30 | OAN_CTX: ORG/CHANNEL viewer, ROLES, in_group | Database | 1.5 | P0 | Done
1.31 | Staff scopes + single authz + one grant API | Database | 1.5 | P0 | Done
1.33 | Retention rules + injectable clock | Database | 1 | P0 | Done
1.34 | Automations map, DBMS_LOCK run locks, send state machine | Database | 1.5 | P0 | Done
1.35 | Messaging permission, referral opt-in, directory switch | Database | 0.5 | P1 | Done
1.36 | oan_export_pkg (person-level exports) | Database | 1 | P0 | Done
1.37 | option_live(): Build Option + DPIA sign-off | Database | 0.75 | P0 | Done
1.6 | Personal-data registry + test | Database | 0.75 | P0 | Done
1.7 | Seed reference data | Database | 2 | P0 | Done
1.8-1.13 | Audit, context, visibility macro, views, security, auth packages | Database | 10.75 | P0 | Done
W0.1 | Login, create account, confirm email, reset password | W0 Auth & admin | 2.5 | P0 | Done
W0.19 | Suggest term, request a chapter | W0 Auth & admin | 0.5 | P1 | Done
W0.2 | Welcome, legal, IP report | W0 Auth & admin | 1.5 | P0 | Done
W0.3 | Application status, re-accept terms | W0 Auth & admin | 1.5 | P0 | Done
W0.4 | Link existing account, confirm identity | W0 Auth & admin | 1.5 | P0 | Done
W0.5 | Membership application | W0 Auth & admin | 1 | P0 | Done
W0.6 | Access denied | W0 Auth & admin | 0.25 | P0 | Done
W0.7 | oan_chat_pkg onboarding logic | W0 Auth & admin | 3 | P0 | Done
W0.8 | Onboarding conversation (Page 2) | W0 Auth & admin | 2.5 | P0 | Done
W1.1 | Global page: rail, profile card, badge, search | W1 Shell | 1.5 | P1 | Done
W1.2 | Home: greeting, letters carousel, What's new, route cards | W1 Shell | 2 | P1 | Done
W1.3 | Global search results (Page 19) | W1 Shell | 1.5 | P1 | Done
W2.1 | Profile, CV and career-status tables | W2 Profile & directory | 2.5 | P1 | Done
W2.11 | Profile-update nudge (08:00 local) | W2 Profile & directory | 0.75 | P1 | Done
W2.2 | Profile package extensions | W2 Profile & directory | 1.5 | P1 | Done
W2.3 | Directory index (sync tightening, 2-min refresh) | W2 Profile & directory | 5.5 | P1 | Done
W2.4 | My profile + member profile | W2 Profile & directory | 2.5 | P1 | Done
W2.5 | Directory search + results (Pages 20, 21) | W2 Profile & directory | 3 | P1 | Done
W2.6 | My CV + current work profile (Pages 24, 25, J-20) | W2 Profile & directory | 3 | P1 | Done
W2.7 | CV share/revoke, last 3 versions | W2 Profile & directory | 1 | P1 | Done
W2.8 | Connections: connect, follow, block (Page 28) | W2 Profile & directory | 3.5 | P1 | Done
W3.1 | Insights and article rules, saves, views | W3 Content & events | 2 | P1 | Done
W3.2 | Library, item, submit, saved, tag follow | W3 Content & events | 3 | P1 | Done
W3.3 | Events package: capacity, waitlist, .ics | W3 Content & events | 3 | P1 | Done
W3.4 | Events + event detail (Build Pack content pages 30-33) | W3 Content & events | 3 | P1 | Done
W3.6 | Event reminders (07:00 local) | W3 Content & events | 0.75 | P1 | Done
W4.1 | Messaging package + message search index | W4 Messaging & channels | 6 | P1 | Done
W4.2 | Conversations (two-pane, polling) (Page 40) | W4 Messaging & channels | 3 | P1 | Done
W4.3 | Notifications per channel; centre, preferences, unsubscribe | W4 Messaging & channels | 4 | P1 | Done
W4.5 | Introductions + Help-Me-Connect (Page 29) | W4 Messaging & channels | 4.25 | P1 | Done
W5.2 | Jobs, opportunity feed, applications (Pages 50-55, J-01, J-18) | W5 Jobs & helpdesk | 7 | P2 | Done
W5.3 | Referral request (Page 33, J-08) | W5 Jobs & helpdesk | 2.5 | P2 | Done
W5.4 | Helpdesk; HR documents signpost only (no HR brokering, Q29) | W5 Jobs & helpdesk | 3 | P2 | Done
W5.5 | Skills & demand insights (Page 56, J-02, J-03) | W5 Jobs & helpdesk | 2.75 | P2 | Done
W5.6 | Hourly SLA job | W5 Jobs & helpdesk | 0.5 | P2 | Done

## Delivery Board
OAN Portal Delivery Board - 16 Sprints, 11 Gates (Plan V3.2, Iteration 9, 13 Oct 2026)
Source: attached OAN-Delivery-Board-landscape.pdf. APEX Build Pack V1.1 (Q31) - APEX 26.1.5 (Q32) - no Oracle HR brokering (Q29) - no Oracle logos (Q30). Card status comes from task_plan.md in the GitHub repository.
Board in numbers
Sprints | Gates | Tracked tasks | Dev estimate | Done or authored offline | Blocked | Planned end of S15
16 | 11 | 154 | 319.75 | 70 | 3 | 28 May 2027
S0-S15 | incl. go-live 8.0 | on the board | person-days pd | iteration 23 | mostly on G0
Sprints, S0-S15
Sprint | Window | Phase | Theme and scope | Tasks | Dev pd | Gate(s)
S0 | 19-30 Oct 2026 | SETUP | Toolchain, spikes, migrations | 21 | 18.75 | G0
S1 | 2-13 Nov 2026 | BUILD | First shared DB deploy | 17 | 49.25
S2 | 16-27 Nov 2026 | BUILD | DB tests, W0 auth + admin | 18 | 32.5 | G1, G-RB
S3 | 30 Nov-11 Dec 2026 | BUILD | W0 onboarding, W1 shell | 17 | 27 | G-AI
S4 | 14-25 Dec 2026 | BUILD | W2 profile + directory | 5 | 13
S5 | 28 Dec 2026-8 Jan 2027 | BUILD | W2 CV, privacy; demo 1 | 10 | 21.25
S6 | 11-22 Jan 2027 | BUILD | W3 content, W4 messaging | 12 | 26.25 | G-CH
S7 | 25 Jan-5 Feb 2027 | BUILD | W4 channels, W5 orgs | 6 | 24.75 | G-CF
S8 | 8-19 Feb 2027 | BUILD | W5 jobs, helpdesk, W6 experts; demo 2 | 9 | 22 | G2
S9 | 22 Feb-5 Mar 2027 | BUILD | W6 groups, partners, mentoring | 6 | 18
S10 | 8-19 Mar 2027 | BUILD | W6 training, initiatives; demo 3; buffer | 5 | 13.25 | G3
S11 | 22 Mar-2 Apr 2027 | BUILD + DESCOPE | W7 reports; descope lane | 9 | 26
S12 | 5-16 Apr 2027 | HARDENING + UAT | Load, WCAG, security, UAT | 7 | 18 | G4, G5
S13 | 19-30 Apr 2027 | GO-LIVE GATE | Gate 8.0, PROD release | 7 | 5.75 | 8.0
S14 | 3-14 May 2027 | PILOT | Pilot ~50 members, every staff role, >= 3 orgs | 1 | 0
S15 | 17-28 May 2027 | HYPERCARE | Hypercare + handover | 4 | 4
Total |  |  |  | 154 | 319.75
Progress by workstream (iteration 23)
Workstream | Done | Total | Progress
WS0 Environment | 11 | 23 | 47.83%
WS1 Database | 15 | 20 | 75%
W0 Auth & admin | 9 | 22 | 40.91%
W1 Shell & Home | 3 | 3 | 100%
W2 Profile & directory | 9 | 11 | 81.82%
W3 Insights & events | 5 | 6 | 83.33%
W4 Conversations | 4 | 6 | 66.67%
W5 Opportunities | 5 | 7 | 71.43%
All workstreams | 61 | 98 | 62.24%
Board status legend (left border colour on the attached board)
Status | Meaning | On the attached board
Not started | Not begun; open in a future sprint. |  |  |  |  | Grey
In progress | Actively being worked this sprint. |  |  |  |  | Amber
Authored offline (validated, not live) | Written and validated locally; not yet deployed. |  |  |  |  | Blue
Blocked | Cannot proceed; mostly waiting on G0 (ADMIN bootstrap, OAuth client). |  |  |  |  | Red
Gated by Build Option | Built with the Build Option on in DEV; switched on in PROD only after DPIA sign-off and the external gate. |  |  |  |  | Purple
Done | Complete and accepted. |  |  |  |  | Green
- Estimates are developer person-days (pd) before the 20% contingency.
- Tiers P0-P4 come from docs/05-flow-priority.md: P0 and P1 are never cut; the S11 descope lane cuts from P4 upward.
- Gated items are built with their Build Option on in DEV only, and switched on in PROD only after the DPIA sign-off and the external gate.
- Planned end of S15 is 28 May 2027.

## Gate Checklist
Gate Checklist - 11 Gates incl. Go-Live 8.0
Every gate, its due date, its status and the condition that must be met. Gates are explicit decision points: no gate is passed without its condition.
Gate | Due | Status | Condition
G0 | End S0 - 19-30 Oct | In progress | Done: toolchain, dev ADB aiatp on APEX 26.1.5 (Q32), ADMIN bootstrap, install, utPLSQL, spikes (13 Oct); app 200 live on dev with 51 pages (14 Oct). Open: Google OAuth set aside (Q33), staffing decision.
G1 | End S2 - 16-27 Nov | Pending | Content inventory + owner; product owner signs off the Must/Should/Could AC list.
G-RB | End S2 - 16-27 Nov | Pending | Re-baseline: S1-S2 velocity and offline-rework actuals vs plan; invoke descope lane if < 20 pd/sprint.
G-AI | End S3 - 30 Nov-11 Dec | Pending | AI_ASSISTANT DPIA annex + GenAI DPA signed.
G-CH | End S6 - 11-22 Jan | Pending | Slack app, WhatsApp Business + templates, Slack/Meta DPAs, CHANNELS DPIA annex.
G-CF | End S7 - 25 Jan-5 Feb | Pending | CAREERS_FEED DPIA annex + feed terms.
G2 | End S8 - 8-19 Feb | Pending | Region decided; temporary 100k load-test ADB booked.
G3 | End S10 - 8-19 Mar | Pending | All staff-role holders named with IdP + 2-step verification; >= 3 pilot orgs verified.
G4 | End S12 - 5-16 Apr | Pending | Legal texts, privacy contact, compliance workstream complete.
G5 | End S12 - 5-16 Apr | Pending | Final UAT (J-01..J-21 regression) signed by the product owner.
8.0 | S13 - 19-30 Apr | Pending | Go-live gate: 18 checks incl. DPIA per option, secrets, ORDS exposure, every Must AC.
Gate groups
Build-option gates (G-AI, G-CH, G-CF) | Each gated Build Option needs its own DPIA annex and its external agreement signed before it is switched on in PROD.
Re-baseline gate (G-RB) | Invokes the descope lane if measured velocity falls below 20 pd per sprint across S1-S2.
Release gates (G4, G5, 8.0) | Compliance complete, final UAT signed, then the 18-check go-live gate.
Post-go-live (S14 pilot, S15 hypercare) | Pilot with ~50 members covering every staff role and >= 3 partner organisations, then two weeks of hypercare and handover.

## Kanban Board
Delivery Kanban - OAN Portal Build Backlog by Status
One card per work item, in the six status columns of the attached delivery board. Columns run Not started > In progress > Authored offline > Blocked > Gated > Done. Full card list on the Board Tasks tab.
65 Not started | 13 In progress | 9 Authored offline (validated, not live) | 3 Blocked | 3 Gated by Build Option | 59 Done
100 pd | 43.75 pd | 17.75 pd | 3 pd | 15 pd | 137 pd
0.16a 1.5 pd | 0.15 1.0 pd | 1.32 0.5 pd | 0.12 1.0 pd | W0.9 3.0 pd | 0.1 0.5 pd
Liquibase changelog (forward-only) | Secrets register (all secrets, owners, rotation) | OAN_LU_CODE intents with live_yn | Spike: social sign-in, switch in session, re-auth | AI assistant (read-only, opt-in) | Node, JDK 21, SQLcl 26.2 installed
Environment ¦ P0 | Environment ¦ P0 | Database ¦ P1 | Environment ¦ P0 | W0 Auth & admin ¦ P4 | Environment ¦ P0
0.16c 0.5 pd | 0.9 2.5 pd | M.2 3.5 pd | 0.17 1.5 pd | W4.4a 6.0 pd | 0.10 0.25 pd
Scratch-schema rebuild each sprint | CI: base-table scan, authz, utPLSQL, gitleaks, validate, page registry, brand | Groups refactor: forums -> groups / posts / comments | Spike: webhook HMAC + async job < 1s | Slack channel | Spike: APEX version on dev and PROD
Environment ¦ P0 | Environment ¦ P0 | Migration ¦ P1 | Environment ¦ P4 | W4 Messaging & channels ¦ P4 | Environment ¦ P0
0.18 0.5 pd | 1.23 1.5 pd | W0.10 2.0 pd | 0.6 0.5 pd | W4.4b 6.0 pd | 0.11 1.0 pd
Spike: APEX GenAI service | Jobs package (fix failure link -> 1075) | Approval queue + application review | Google OIDC client | WhatsApp channel + channel settings (Page 43) | Spike: two-schema calls incl. ORDS
Environment ¦ P4 | Database ¦ P0 | W0 Auth & admin ¦ P0 | Environment ¦ P0 | W4 Messaging & channels ¦ P4 | Environment ¦ P0
0.19 OAN | 1.26 4.0 pd | W0.11 3.0 pd |  |  | 0.13 0.5 pd
Procure Slack app, WhatsApp Business | utPLSQL suites (R01, R16, R19/20, R26, secrets) | Members, staff roles, scopes |  |  | Spike: PBKDF2 210k under load
Environment ¦ P4 | Database ¦ P0 | W0 Auth & admin ¦ P0 |  |  | Environment ¦ P0
0.1b 1.0 pd | 1.28 2.5 pd | W0.12 1.5 pd |  |  | 0.14 0.5 pd
Local Oracle DB Free + utPLSQL (optional) | Synthetic data: 100k profiles, 1M posts, 20k jobs | Chapters + chapter requests |  |  | Spike: Oracle Text on ADB
Environment ¦ P4 | Database ¦ P0 | W0 Auth & admin ¦ P0 |  |  | Environment ¦ P0
0.20 1.0 pd | W0.15 2.0 pd | W0.13 2.0 pd |  |  | 0.16b 0.75 pd
ORDS install: OAN_API schema, channel modules | Audit log, report modal, my decisions | Lookups / taxonomy admin |  |  | Deploy wrapper + live validate gate
Environment ¦ P4 | W0 Auth & admin ¦ P0 | W0 Auth & admin ¦ P0 |  |  | Environment ¦ P0
0.7 0.5 pd | W0.18 7.5 pd | W0.14 2.5 pd |  |  | 0.2 0.5 pd
OCI Email Delivery + APEX SMTP | Shared components + security baseline | Moderation queue + appeals |  |  | Dev ADB (APEX 26.1.5, Q32), synthetic data
Environment ¦ P0 | W0 Auth & admin ¦ P0 | W0 Auth & admin ¦ P0 |  |  | Environment ¦ P0
1.29 1.5 pd | W2.10 2.5 pd | W0.21 2.0 pd |  |  | 0.3 1.0 pd
Traceability + Must/Should/Could AC tags | Profile update + privacy request admin (Page 121) | OAN_CHAT_API + OAN_NOTIFY_API (Build Pack contracts) |  |  | ADMIN bootstrap: schemas, grants, OAN_CTX, sign-in hosts
Database ¦ P0 | W2 Profile & directory ¦ P0 | W0 Auth & admin ¦ P0 |  |  | Environment ¦ P0
5.1 4.0 pd | W2.9 5.0 pd | W0.22 0.75 pd |  |  | 0.4 0.5 pd
Full AC regression + evidence pack | Account settings + privacy centre | Build Pack conventions: AI_ items, IS_* names, Build Pack options |  |  | Workspace probe, deployment files, SQLcl connections
Quality ¦ P0 | W2 Profile & directory ¦ P0 | W0 Auth & admin ¦ P0 |  |  | Environment ¦ P0
5.10 3.0 pd | W3.5 5.0 pd |  |  |  | 0.5 0.25 pd
J-01..J-21 end-to-end regression | Library moderation, import, events admin |  |  |  | Git repo, layout, .gitignore
Quality ¦ P0 | W3 Content & events ¦ P1 |  |  |  | Environment ¦ P0
5.2 3.0 pd | W5.1 4.5 pd |  |  |  | 0.8 0.25 pd
Security test (ZAP, bypass, leaks) | Organisations: application, verification (Pages 55, 1025) |  |  |  | utPLSQL on dev
Quality ¦ P0 | W5 Jobs & helpdesk ¦ P2 |  |  |  | Environment ¦ P0
5.3a 1.0 pd | W5.7 0.75 pd |  |  |  | 1.1-1.5 7.25 pd
100k directory smoke test | Careers deep-links (feed gated, G-CF) |  |  |  | DDL: identity, profile, chapters, content, ops
Quality ¦ P1 | W5 Jobs & helpdesk ¦ P2 |  |  |  | Database ¦ P0
5.3b 3.0 pd | W6.1 5.0 pd |  |  |  | 1.14-1.22 15.0 pd
Full load test on temporary ADB | Groups governance, reactions, stories, private search |  |  |  | Registration, profile, taxonomy, library, files, groups, moderation, notify, privacy
Quality ¦ P0 | W6 Community & partners ¦ P1 |  |  |  | Database ¦ P0
5.3c 1.0 pd |  |  |  |  | 1.24 2.0 pd
Load test re-run |  |  |  |  | Text/search split (search_body, directory index)
Quality ¦ P0 |  |  |  |  | Database ¦ P1
+ 51 more on the Board Tasks tab |  |  |  |  | + 47 more on the Board Tasks tab
How this board works
- Board totals: 154 tracked tasks and 319.75 pd of development estimate across the 16 sprints S0-S15.
- 31 cards are Done or Authored offline (validated, not live); 6 are Blocked, mostly waiting on G0 (ADMIN bootstrap and the Google OAuth client).
- Gated cards are built with their Build Option on in DEV only, and switched on in PROD only after their DPIA annex and external agreement are signed.
- Estimates are developer person-days before the 20% contingency. P0 and P1 are never cut; the S11 descope lane cuts from P4 upward.
- The Kanban Dashboard tab counts these cards live; the Delivery Board tab carries the sprint and gate structure.

## Kanban Dashboard
Kanban Dashboard - Board Flow, Effort and Priority
Live from the Board Tasks tab. Sprint and gate structure sits on the Delivery Board tab; capacity and velocity on the Sprint Planner Dashboard tab.
Items on board | Dev estimate (pd) | Done | Authored offline | In progress | Blocked | Gated | Not started
153 | 316.5 | 59 | 9 | 13 | 3 | 3 | 65
1. Cards and effort by status
Status | Cards | Dev pd | % of pd
Not started | 65 | 100 | 31.6%
In progress | 13 | 43.75 | 13.82%
Authored offline (validated, not live) | 9 | 17.75 | 5.608%
Blocked | 3 | 3 | 0.9479%
Gated by Build Option | 3 | 15 | 4.739%
Done | 59 | 137 | 43.29%
2. Effort by category
Category | Cards | Dev pd
Environment | 23 | 17.5
Database | 20 | 57
Quality | 13 | 28.5
Content & adoption | 3 | 2
Compliance | 10 | 0
Release | 7 | 3.25
Acceptance | 9 | 16.5
Migration | 2 | 5
W0 Auth & admin | 22 | 43
W1 Shell | 3 | 5
W2 Profile & directory | 11 | 30.75
W3 Content & events | 6 | 16.75
W4 Messaging & channels | 6 | 29.25
W5 Jobs & helpdesk | 5 | 17.75
W6 Community & partners | 9 | 36.75
W7 Reporting | 3 | 7.5
3. Cards by priority tier
Priority | Cards | Dev pd | Meaning
P0 | 98 | 164.75 | Critical path - never cut
P1 | 30 | 75.75 | Never cut
P2 | 8 | 25.25 | Committed
P3 | 6 | 26.75 | Committed - first to flex
P4 | 10 | 24 | Descope lane - cut first

## Sprint Planner Dashboard
Sprint Planner Dashboard - Attached Capacity & Performance Charts
Ports the live charts from the attached 'Sprint Capacity Planner & Performance Tracker.xlsx' into this plan. Series are linked to the Sprint Capacity Planner and Sprint Performance Tracker tabs.
Attachment
Attached source |  | Sprint Capacity Planner & Performance Tracker.xlsx
How it is attached |  | Its Capacity Planner, Performance Tracker and dashboard charts are integrated into this workbook (Sprint Capacity Planner, Sprint Performance Tracker and Sprint Planner Dashboard tabs).
Refresh |  | Edit inputs on the Sprint Capacity Planner tab; the tracker formulas and these charts recalculate automatically.
1. Commitment vs delivery by sprint (Performance Tracker)
Sprint | Committed (SP) | Delivered (SP) | Completion % | 3-sprint avg
Sprint 1 | 32 | 27 | 84.38% | 27
Sprint 2 | 34 | 30 | 88.24% | 28.5
Sprint 3 | 30 | 25 | 83.33% | 27.3333
Sprint 4 | 36 | 33 | 91.67% | 29.3333
Sprint 5 | 33 | 29 | 87.88% | 29
Sprint 6 | 38 | 35 | 92.11% | 32.3333
Sprint 7 | 35 | 33 | 94.29% | 32.3333
Sprint 8 | 40 | 37 | 92.5% | 35
Sprint 9 | 37 | 35 | 94.59% | 35
Sprint 10 | 42 | 39 | 92.86% | 37
Sprint 11 | 39 | 37 | 94.87% | 37
Sprint 12 | 44 | 42 | 95.45% | 39.3333
2. Capacity and forecast (Capacity Planner + Tracker)
Current sprint capacity (SP) | Risk-adjusted capacity (SP) | Recommended commitment (SP) | Average completion rate | Next sprint forecast (SP)
53.75 | 48.375 | 48.375 | 91.01% | 41.6364
3. Resource story-point capacity - current sprint (Capacity Planner)
Resource | Role | Hours available | Story-point capacity | Allocation %
Resource 1 | Product Owner | 23 | 2.875 | 0.5
Resource 2 | Scrum Master / Delivery Lead | 23 | 2.875 | 0.5
Resource 3 | UX Lead | 63 | 7.875 | 1
Resource 4 | UI / Visual Designer | 63 | 7.875 | 1
Resource 5 | Design Systems / Front-end | 63 | 7.875 | 1
Resource 6 | Back-end Engineer | 63 | 7.875 | 1
Resource 7 | Solution Architect | 23 | 2.875 | 0.5
Resource 8 | Accessibility / QA Lead | 63 | 7.875 | 1
Resource 9 | Content Strategist | 23 | 2.875 | 0.5
Resource 10 | Change & Comms Lead | 23 | 2.875 | 0.5

## Status Report
Project Status Report - OAN Portal (as of 15 October 2026 (iteration 23))
Oracle APEX application 200 on Autonomous Database - Plan v3.2 - APEX Build Pack v1.1 - development environment only. Source: OAN-Project-Status-Report.pdf.
Summary
The portal is well ahead of plan. Sprint S0 formally starts on 19 October, yet the database platform and waves W0 to W5 already run on the dev environment: sign-in and onboarding, the member shell and Home, profiles, directory and CV, insights and events, conversations and notifications, opportunities, referrals, helpdesk and skills in demand, plus company registration for partners and other employers.
Every change is validated, tested on the database and pushed to GitHub, where CI runs on each push.
MAIN RISK: admin pages cannot be tested end to end because staff roles need Google or LinkedIn sign-in (NFR-01) and Google sign-in is set aside (Q33). Email delivery (task 0.7) is not set up, so emails are queued but not delivered on dev. Slack and WhatsApp are built but stay off until gate G-CH.
Progress at a glance
APEX pages live on dev | Database tests passing | Test suites | Person-days of plan done
73 | 147 | 16 | 140
Person-days of plan done | Plan person-days before contingency | Progress vs plan | Blocked or gated | Tasks on board
140 | 320 | 43.75% | 6 | 154
Board status distribution (154 tracked tasks)
Status | Tasks | % of board | Source
Done | 61 | 39.61% | Status report / board (iter 23)
In progress | 13 | 8.442% | Status report / board (iter 23)
Authored, untested | 9 | 5.844% | Status report / board (iter 23)
Blocked | 3 | 1.948% | Status report / board (iter 23)
Gated by build option | 3 | 1.948% | Status report / board (iter 23)
Not started | 65 | 42.21% | Status report / board (iter 23)
Total | 154 | 100%
Progress by workstream
Workstream | Status | What is in place
WS0 Environment | 11 of 23 done | Dev ADB on APEX 26.1.5, ADMIN bootstrap, utPLSQL, spikes. Blocked: Google client, social sign-in spike, email delivery.
WS1 Database | 15 of 20 done | 100 tables, 126 secure views, 39 packages; personal-data registry with retention rules; staff scopes; job run locks; synthetic data.
W0 Auth & admin | 9 of 22 done | Sign-in, registration, onboarding chat, legal, identity confirmation; admin pages built but untested (no admin login).
W1 Shell & Home | 3 of 3 done | Rail, profile card, search, notifications badge; Home with letters, upcoming events and What's new.
W2 Profile & directory | 9 of 11 done | Directory index, cards with Follow and Message, profiles, CV sections, sharing and printing, work profile, introductions, recommendations, reminders.
W3 Insights & events | 5 of 6 done | Insights and perspectives with saves; events with registration, waitlist, calendar file, reminders and check-in.
W4 Conversations | 4 of 6 done | Conversations with search and polling, notification settings, unsubscribe, Help Me Connect. Slack and WhatsApp built, gated (G-CH).
W5 Opportunities | 5 of 7 done | Opportunities, applications with optional CV, referrals, helpdesk, skills in demand; company registration and workspace.
W6-W7, quality, release | next | Community groups, experts, mentoring, training, partner talent requests; then administration and hardening.
Decisions and actions needed
Item | Impact | Owner | Status
Google OAuth client, or a dev-only admin login | Blocks testing of admin pages, company verification and moderation (NFR-01) | OAN / product owner | Open
OCI Email Delivery for dev (task 0.7) | Limits sign-up confirmation, password links, company approval emails | OAN | Open
Gate G-CH: Slack app, WhatsApp Business number, DPAs, DPIA annex | Gated channels are built but switched off | OAN | Open
Gate G-CF: Oracle Careers feed | Gated Oracle roles are entered as Careers links until then | OAN | Open
PBKDF2 cost (~1.9 s per sign-in at 210k iterations) | Change request: NFR-01 vs login performance | Product owner | Open
Staffing decision (G0) | Open one vs two developers sets the end date | Sponsor | Open
Dev deploy secrets (wallet and passwords) | Deployment to dev stays manual until the owner adds them | OAN | Open
Next steps
- W6: community groups, experts and Ask-the-Expert, mentoring with capacity, training and certificates, partner talent requests and candidate feedback (pages 60-72).
- W7: administration and hardening (pages 100-113), including profile-update and privacy-request admin, library import and channel administration.
- Product-owner demo of W0-W5 once an admin sign-in path is agreed.
Delivery facts
Live board | maheashtiwarrii-dev.github.io/OAN_APP_Portal
Printable board | docs/OAN-Delivery-Board-landscape.pdf
GitHub Project | projects/1 (168 items)
Database objects | 100 tables, 126 secure views, 39 packages
Local release checks | 115 queries and 153 PL/SQL blocks compiled as the app schema; utPLSQL; import to dev
Test data | Synthetic only (Q12): 265 alumni, test accounts, 23 CV-based personas; no Oracle HR documents (Q29, Q35)
Production deployment | Not automated - requires go-live gate 8.0

## Delivered Pages
Delivered Pages on Dev - 73 pages in Application 200
The pages already built and running on the development environment, by area (status report, 15 Oct 2026).
Area | Pages
Sign-in and onboarding | 1 Login - 2 Onboarding - 3 Create account - 4 Access denied - 5 Status - 6 Application - 7 Confirm email - 8 Reset password - 9 Link account - 11 Welcome - 12 Legal - 13 Report a concern - 14 Accept terms - 15 Confirm identity - 44 Unsubscribe
Shell and Home | 0 Global page - 10 Home - 19 Search - 41 Notifications - 42 Notification settings - 43 Slack and WhatsApp
Profile and directory | 20 Directory - 21 Results - 22 Member profile - 23 My profile - 24 My CV - 25 Work profile - 26 Settings - 27 Privacy centre - 28 My network - 29 Help Me Connect - 90 - 91 - 231-234
Insights and events | 30 Insights - 31 Article - 301 Write - 32 Events - 33 Event detail - 331 Event editor - 34-36 Library
Conversations and community | 40 Conversations - 60 Discussions - 62 Post - 73 New post - 80 Report - 81 My decisions
Careers and helpdesk | 50 Opportunities - 51 Opportunity - 52 My applications - 53 Post - 54 Referrals - 55 Helpdesk - 56 Skills in demand
Companies | 76 Register your company (public) - 70 Company workspace - 71 Company opportunities - 112 Company registrations (admin)
Administration (untested) | 101 Members - 106 Taxonomy - 107 Moderation (incl. job review) - 110 Audit - 114 Approvals - 115 Review - 116 Member detail - 117 Chapters - 118 Requests - 119 Appeals
- 73 APEX pages are live on dev; every page is validated with SQLcl before import (offline APEXLang validation).
- Administration pages are built but untested end to end: staff roles need Google or LinkedIn sign-in (NFR-01) and Google sign-in is set aside (Q33).
- Slack and WhatsApp (page 43) are built but switched off until gate G-CH.

## CI-CD Pipeline
CI/CD Pipeline - Build, Validate, Deploy and Publish
Every push and pull request runs the pipeline; deployment to dev is manual and production deployment waits for go-live gate 8.0.
Stage | What runs | State
1 - Push / pull request | Brand check (no Oracle logos) - Link check (no 404 pages) - Base-table check (NFR-03) - Dev-script guard - Secret scan (gitleaks) | Live
2 - Build | Offline APEXLang validation with SQLcl (all 73 pages); no database or secrets needed | Live
3 - Deploy to dev (manual) | Validate again - Import app 200 - Run utPLSQL suites - Smoke-test sign-in page | Live
4 - Publish | Kanban board, status report and both PDFs to GitHub Pages; GitHub Project kept in step | Live
Pipeline items
Item | Status
Workflows ci.yml, deploy-dev.yml, board.yml | Live - CI green on every push this week
Check scripts (ci/) | Live - links, base tables, brand and validation pass on 73 pages
Board, report and PDFs on GitHub Pages | Live - republished on every push to docs/
Local release checks per iteration | Running - 115 queries and 153 PL/SQL blocks, utPLSQL, import to dev
Dev deploy secrets | Pending - wallet and passwords to be added by the owner in environment dev
Production deployment | Not automated - requires go-live gate 8.0